## KET
Part name | Responsible/contact department | Availability | units | Instore quantity | quantity to deliver | already delivered? | Picture | Notes
Battery combiner panel (BCP) | AM_ENG | in store | item |  | 1 | yes
Power conversion system (PCS) | AM_ENG | in store | item |  | 1 | yes
cable 4 core 240mm | AM_ENG | procure | meter |  |  | no
cable 4 core 70mm | AM_ENG | in store_from TLH | meter |  |  | no
cable 16mm green_yellow (one just arrived) | AM_ENG | in store | meter |  | 100m | yes |  | Earthing each PCS and battery rack + combiner boxes to main db. reserved for MAT/TLH but can be taken to any urgent site
cable 2 core 1.5mm | AM_ENG | procure | meter |  | 40m | no
Hwuawei Inverter | AM_ENG | in store | item |  | 3 | yes
cable 2 core 1.5mm Inverter comms (Black) | AM_ENG | in store | meter |  | 14m | yes |  | cut from drum by fencing materials
cable 4 core 35mm Inverter power (Black) | AM_ENG | in store | meter |  | 40m | yes |  | cut from drum by fencing materials
SPD combiner box | AM_ENG | in store | item |  | 3 | yes
Small Battery Rack | AM_ENG | in store | item |  | 3 | yes
Battery (SYL) | AM_ENG | in store | item |  | 48 | yes
Battery to BCP DC cables 25mm (Orange) | AM_ENG | in store | meter |  | 3 positive 3 negative ~10m long (precut) | yes |  | Was in a ENERGY storage system 'Accessories' box
BCP to PCS DC cables 25mm (Orange) | AM_ENG | in store | meter |  | 53m | yes |  | cut from drum by fencing materials
Small site battery parts bag | AM_ENG | in store | item |  | 3 | yes |  | Was in a ENERGY storage system 'Accessories' box
cable 6mm(Black) | AM_ENG | procure | meter |  | 50m | no
Main DB | AM_ENG | procure | item |  | 1 | no
cable 2 core 4mm | AM_ENG | procure | meter |  | 10m | no
cable Airdac 10mm | AM_ENG | procure or ask for OnM | meter |  | 15m | no
50mm PVC conduit | AM_ENG | procure | meter |  | 500mm | no
50mm PVC adapter | AM_ENG | procure | item |  | 3 | no
25mm PVC conduit | AM_ENG | procure | meter |  | 6m | no
25mm Flexible PVC conduit | AM_ENG | procure | meter |  | 5m | no
25mm adapter | AM_ENG | procure | item |  | 4 | no
25mm coupler | AM_ENG | procure | item |  | 11 | no
10mm*6 lug | AM_ENG | procure | item | 3 | 2 | no
16mm*8 lug | AM_ENG | procure | item | 35 | 31 | no
25mm*8 lug | AM_ENG | procure | item | 10 | 8 | no
35mm*8 lug | AM_ENG | procure | item | 30 | 24 | no
70mm*10 lug | AM_ENG | procure | item |  | 38 | no
ALU120-300mm Lug torque shear lug | AM_ENG | procure | item | 5 | 9 | no
20A small round fuse | AM_ENG | procure | item |  | 2 | no
1.5mm ferrule | AM_ENG | procure | item |  | 10 | no
2.5mm ferrule | AM_ENG | procure | item |  | 17 | no
4mm ferrule | AM_ENG | procure | item |  | 6 | no
6mm ferrule | AM_ENG | procure | item |  | 48 | no
10mm ferule | AM_ENG | procure | item |  | 48 | no
25mm line tap | AM_ENG | procure | item |  | 3 | no
70mm line tap | AM_ENG | procure | item | 5 | 2 | no
HVAC outdoor unit | AM_ENG | in store | item |  | 2 | yes
HVAC indoor unit | AM_ENG | in store | item |  | 2 | yes
PV entry plate | AM_Prod | in store | item |  | 1 | yes
PV entry plate cover | AM_Prod | in store | item |  | 1 | yes
No. 00 glands PVC | AM_ENG | in store | item |  | 24 | no
M6 x 20mm Hex bolt | AM_ENG | in store | item |  | 8 | no
M6 Hex nut | AM_ENG | in store | item |  | 8 | no
M8 x 20mm Hex bolt | AM_ENG | in store | item |  | 6 | no
M8 x 30mm Hex bolt | AM_ENG | in store | item |  | 40 | no
M8 Hex nut | AM_ENG | in store | item |  | 40 | no
M8 washer | AM_ENG | in store | item |  | 54 | no
M10 Hex nut | AM_ENG | in store | item |  | 52 | no
M10 Large washer | AM_ENG | in store | item |  | 12 | no
M10 x 80mm hex bolt | AM_ENG | in store | item |  | 12 | no
M12 threaded rod | AM_ENG | procure | item |  | 2m | no
M12 bolt and nuts | AM_ENG | procure | item |  | 48 | no
Epoxy glue | AM_ENG | procure | item |  | small bottle | no
plug top | AM_ENG | procure | item |  | 6 | no
Powerhouse CPU | AM_IT | confirm with IT | item |  | 1 | no
Powerhouse PC screen | AM_IT | confirm with IT | item |  | 1 | no
Wifi router | AM_IT | confirm with IT | item |  | 1 | no
ethernet cable | AM_IT | confirm with IT | meter |  | 40m | no
ethernet cable head | AM_IT | confirm with IT | item |  | 6 | no
Cable trays 3m | AM_ENG | in store | item |  | 10 | yes
Cable tray corner | AM_ENG | in store | item |  | 1 | yes
cable tray mount | AM_ENG | in store | item |  | 30 | yes
Cable tray joiner | AM_ENG | in store | item |  | 25 | yes
Cable tray Hanger | AM_Prod | confirm with prod | item |  | 1 | yes
M10 threaded rod (ones outside now) | AM_ENG | in store | meter |  | 3m x 1/ 1m x 3 | no
M10 nuts for threaded rod | AM_ENG | procure | item |  | 40 | no
clip-on rail | AM_ENG | in store | meter |  | 1m x 1 | no
No 4 gland SWA | AM_ENG | to procure | item |  | 6 | no
No 4 shround | AM_ENG | to procure | item |  | 6 | no
No 6 gland SWA | AM_ENG | to procure | item |  | 1 | no
No 6 shroud | AM_ENG | to procure | item |  | 1 | no
No 0 gland PVC | AM_ENG | to procure | item |  | 6 | no
No 2 gland Nylon | AM_ENG | to procure | item |  | 4 | no
No 3 gland Nylon | AM_ENG | to procure | item |  | 1 | no
No 4 gland Nylon | AM_ENG | to procure | item |  | 4 | no
cable 25mm bare copper | AM_ENG | MAS (approx 300m) | item |  | ? | no
cable 70mm bare copper | AM_ENG | in store | meter |  | 125m - 25MM BARE COPPER | yes
cable 70mm housewire green_yellow | AM_ENG | in store | meter |  | 10m | yes
cable 70mm flexible green_yellow | AM_ENG | in store | meter |  | 20m | yes
air spike | AM_ENG | procure | item |  | 2 | no
earth spike | AM_ENG | procure | item |  | 12 | no
earth clamp | AM_ENG | procure | item |  | 15 | no
mc4 females | AM_ENG | procure | item |  | 24 | yes
mc4 males | AM_ENG | procure | item |  | 24 | yes
Network Control Unit (NCU) | AM_ENG | procure | item |  | 1 | no
Tracker Control Unit (TCU) | AM_ENG | procure | item |  | 1 | no
NCU anemometer | AM_ENG | procure | item |  | 1 | no
Heat shrink box for various sizes of terminations | AM_ENG | instore_ENG | item |  | 1 | yes
Curtain wall brackets | AM_PROD | confirm with prod | item |  | 10 | yes
Curtain wall strips | AM_PROD | confirm with prod | item |  | Need to confirm with MAT team | yes
Curtain wall strip mounts | AM_PROD | confirm with prod | item |  | 9 | yes
Roof truss room dividers | AM_PROD | confirm with prod | item |  | 1 large 1 small | no
4.8*18mm Large flange rivets | AM_ENG | procure | item |  | 100 | no

## SEH
Part name | Responsible/contact department | Availability | units | Instore quantity | quantity to deliver | already delivered? | Picture | Notes
Battery combiner panel (BCP) | AM_ENG | in store | item |  | 1 | yes
Power conversion system (PCS) | AM_ENG | in store | item |  | 1 | yes
cable 16mm (G/Y) (one just arrived) | AM_ENG | in store | meter |  | 100m | yes |  | Earthing each PCS and battery rack + combiner boxes to main db. reserved for MAT/TLH but can be taken to any urgent site
cable 2 core 1.5mm | AM_ENG | procure | meter |  | 40m | no
cable 4 core 240mm | AM_ENG | procure | meter |  |  | no
cable 4 core 70mm | AM_ENG | in store_from TLH | meter |  |  | no
Hwuawei Inverter | AM_ENG | in store | item |  | 3 | yes
cable 2 core 1.5mm Inverter comms (Black) | AM_ENG | in store | meter |  | 14m | yes |  | cut from drum by fencing materials
cable 4 core 35mm Inverter power (Black) | AM_ENG | in store | meter |  | 40m | yes |  | cut from drum by fencing materials
SPD combiner box | AM_ENG | in store | item |  | 3 | yes
Small Battery Rack | AM_ENG | in store | item |  | 3 | yes
Battery (SYL) | AM_ENG | in store | item |  | 48 | yes
Battery to BCP DC cables 25mm (Orange) | AM_ENG | in store | meter |  | 3 positive 3 negative ~10m long (precut) | yes |  | Was in a ENERGY storage system 'Accessories' box
BCP to PCS DC cables 25mm (Orange) | AM_ENG | in store | meter |  | 53m | yes |  | cut from drum by fencing materials
Small site battery parts bag | AM_ENG | in store | item |  | 3 | yes |  | Was in a ENERGY storage system 'Accessories' box
cable 6mm(Black) | AM_ENG | procure | meter |  | 50m | no
Main DB | AM_ENG | procure | item |  | 1 | no
cable 2 core 4mm | AM_ENG | procure | meter |  | 10m | no
cable Airdac 10mm | AM_ENG | procure or ask for OnM | meter |  | 15m | no
50mm PVC conduit | AM_ENG | procure | meter |  | 500mm | no
50mm PVC adapter | AM_ENG | procure | item |  | 3 | no
25mm PVC conduit | AM_ENG | procure | meter |  | 6m | no
25mm Flexible PVC conduit | AM_ENG | procure | meter |  | 5m | no
25mm adapter | AM_ENG | procure | item |  | 4 | no
25mm coupler | AM_ENG | procure | item |  | 11 | no
10mm*6 lug | AM_ENG | procure | item | 3 | 2 | no
16mm*8 lug | AM_ENG | procure | item | 35 | 31 | no
25mm*8 lug | AM_ENG | procure | item | 10 | 8 | no
35mm*8 lug | AM_ENG | procure | item | 30 | 24 | no
70mm*10 lug | AM_ENG | procure | item |  | 38 | no
ALU120-300mm Lug torque shear lug | AM_ENG | procure | item | 5 | 9 | no
20A small round fuse | AM_ENG | procure | item |  | 2 | no
1.5mm ferrule | AM_ENG | procure | item |  | 10 | no
2.5mm ferrule | AM_ENG | procure | item |  | 17 | no
4mm ferrule | AM_ENG | procure | item |  | 6 | no
6mm ferrule | AM_ENG | procure | item |  | 48 | no
10mm ferule | AM_ENG | procure | item |  | 48 | no
25mm line tap | AM_ENG | procure | item |  | 3 | no
70mm line tap | AM_ENG | procure | item | 5 | 2 | no
HVAC outdoor unit | AM_ENG | in store | item |  | 2 | yes
HVAC indoor unit | AM_ENG | in store | item |  | 2 | yes
PV entry plate | AM_Prod | in store | item |  | 1 | yes
PV entry plate cover | AM_Prod | in store | item |  | 1 | yes
No. 00 glands PVC | AM_ENG | in store | item |  | 24 | no
M6 x 20mm Hex bolt | AM_ENG | in store | item |  | 8 | no
M6 Hex nut | AM_ENG | in store | item |  | 8 | no
M8 x 20mm Hex bolt | AM_ENG | in store | item |  | 6 | no
M8 x 30mm Hex bolt | AM_ENG | in store | item |  | 40 | no
M8 Hex nut | AM_ENG | in store | item |  | 40 | no
M8 washer | AM_ENG | in store | item |  | 54 | no
M10 Hex nut | AM_ENG | in store | item |  | 52 | no
M10 Large washer | AM_ENG | in store | item |  | 12 | no
M10 x 80mm hex bolt | AM_ENG | in store | item |  | 12 | no
M12 threaded rod | AM_ENG | procure | item |  | 2m | no
M12 bolt and nuts | AM_ENG | procure | item |  | 48 | no
Epoxy glue | AM_ENG | procure | item |  | small bottle | no
plug top | AM_ENG | procure | item |  | 6 | no
Powerhouse PC | AM_IT | confirm with IT | item |  | 1 | no
Powerhouse PC screen | AM_IT | confirm with IT | item |  | 1 | no
Wifi router | AM_IT | confirm with IT | item |  | 1 | no
ethernet cable | AM_IT | confirm with IT | meter |  | 40m | no
ethernet cable head | AM_IT | confirm with IT | item |  | 6 | no
Cable trays 3m | AM_ENG | in store | item |  | 10 | yes
Cable tray corner | AM_ENG | in store | item |  | 1 | yes
cable tray mount | AM_ENG | in store | item |  | 30 | yes
Cable tray joiner | AM_ENG | in store | item |  | 25 | yes
Cable tray Hanger | AM_Prod | confirm with prod | item |  | 1 | yes
M10 threaded rod (ones outside now) | AM_ENG | in store | meter |  | 3m x 1/ 1m x 3 | no
M10 nuts for threaded rod | AM_ENG | procure | item |  | 40 | no
clip-on rail | AM_ENG | in store | meter |  | 1m x 1 | no
No 4 gland SWA | AM_ENG | to procure | item |  | 6 | no
No 4 shround | AM_ENG | to procure | item |  | 6 | no
No 6 gland SWA | AM_ENG | to procure | item |  | 1 | no
No 6 shroud | AM_ENG | to procure | item |  | 1 | no
No 0 gland PVC | AM_ENG | to procure | item |  | 6 | no
No 2 gland Nylon | AM_ENG | to procure | item |  | 4 | no
No 3 gland Nylon | AM_ENG | to procure | item |  | 1 | no
No 4 gland Nylon | AM_ENG | to procure | item |  | 4 | no
cable 25mm bare copper | AM_ENG | MAS | item |  | ? | no
cable 70mm bare copper | AM_ENG | in store | meter |  | 125m - 25MM BARE COPPER | no
cable 70mm housewire (g/y) | AM_ENG | instore | meter |  | 10m | no
cable 70mm flexible (g/y) | AM_ENG | instore_ENG | meter |  | 20m | no
air spike | AM_ENG | procure | item |  | 2 | no
earth spike | AM_ENG | procure | item |  | 12 | no
earth clamp | AM_ENG | procure | item |  | 15 | no
mc4 females | AM_ENG | procure | item |  | 24 | yes
mc4 males | AM_ENG | procure | item |  | 24 | yes
Network Control Unit (NCU) | AM_ENG | procure | item |  | 1 | no
Tracker Control Unit (TCU) | AM_ENG | procure | item |  | 1 | no
NCU anemometer | AM_ENG | procure | item |  | 1 | no
Heat shrink box for various sizes of terminations | AM_ENG | instore_ENG | item |  | 1 | yes
Curtain wall brackets | AM_PROD | confirm with prod | item |  | 10 | yes
Curtain wall strips | AM_PROD | confirm with prod | item |  | Need to confirm with MAT team | yes
Curtain wall strip mounts | AM_PROD | confirm with prod | item |  | 9 | yes
Roof truss room dividers | AM_PROD | confirm with prod | item |  | 1 large 1 small | no
4.8*18mm Large flange rivets | AM_ENG | procure | item |  | 100 | no