## RET items database and tracker
item | item description | unit | quantity procured | quantity balance in store | MAT | TLH | MAS | SHG | LEB | RIB | KET | SEH | TOS | SEB | MAK | BOB | MET | NKU | TLH CLINIC | FAC | EE | HQ | Notes
Stay Rod non adjustable | Stay Rod LV (M12*1.5m) | pcs | 1384 | 951 | 37 | 3 | 89 | 69 |  |  | 32 | 60 | 70 | 20 | 52 |  |  |  | 1
10mm CNE Airdac | 10mm | meters | 39032 | 25492 | MAT: 2000; TLH: 500; MAS: 4000; SHG: 1500; KET: 2500; SEH: 1500; TOS: 1500; MAK: 40
10mm Housewire Black | 10mm | meters | 3750 | 1100 | 300 | 300 | 200 | 200 |  |  | 450 | 200 | 200 | 200 | 500 | [5 empty] | 100
11kV/240 Stepdown Transformer | 11kV/240 Stepdown KL20231120 | pcs | 339 | 47 | MAT: 5; TLH: 25; MAS: 200; KET: 27; SEH: 8; MAK: 24 |  |  |  | 3
11kV/240 Stepdown Transformer | 11kV/240 Stepdown KL20230202 | pcs | 56 | 0 | MAT: 5; TLH: 5; MAS: 32; SHG: 8; MAK: 5 |  |  |  | 1
11kV/240 Stepdown Transformer | 11kV/240 Stepdown KL20231130 | pcs | 3 | 3
3 way PVC junction box | 20mm | pcs | 462 | 402 | TOS: 20; MAK: 40
ABC/ Bundle conductor | ABC/ Bundle conductor single phase | meters | 39266 | 9760 | MAT: 5500; MAS: 5206; SHG: 5506; KET: 4500; SEH: 1706; TOS: 5112; MAK: 1976
ABC strain clamp/ bundle strainer | ABC strain clamp | pcs | 1862 | 1400 | MAT: 17; MAS: 55; SHG: 114; KET: 23; SEH: 100; TOS: 100; MAK: 53
Airdac strain clamp | Large 10-16mm | pcs | 444 | 294 | MAT: 12; MAS: 30; KET: 98; MAK: 10
Airdac strain clamp | Small 4 -10mm | pcs | 6352 | 4434 | MAT: 230; TLH: 10; MAS: 340; SHG: 453; KET: 220; SEH: 250; TOS: 240; MAK: 175
Bare Copper Wire | 70mm | meters | 442 | 0 | MAT: 58; MAS: 52; KET: 301; MAK: 31
Base Plate | Base Plate Stay 450 x450 x 6mm (MV) | pcs | 488 | 308 | MAT: 10; SHG: 23; KET: 94; SEH: 28; MAK: 25
Base Plate | Base Plate Stay 300x300x5mm (LV) | pcs | 1435 | 961 | MAT: 47; MAS: 64; SHG: 42; KET: 168; SEH: 40; TOS: 48; MAK: 65
Base Plate | stay rod base plate | pcs | 39 | 28 | KET: 1; MAK: 10
Bi-metallic Lug | Bi metallic Lug 50mm black | pcs | 200 | 13 | MAT: 28; MAS: 17; KET: 110; MAK: 32
Binding Strap | 30m rolls | pcs | 219 | 193 | MAT: 6; SHG: 1; KET: 7; SEH: 2; TOS: 4; MAK: 6
Bolt Cutter |  | pcs | 24 | 0 | MAT: 2; KET: 20; MAK: 2
Brazing Strap |  | pcs | 91 | 50 | KET: 10; TOS: 5; MAK: 26
Buckles | Strapping Buckles 12.7mm | pcs | 7748 | 6762 | MAT: 100; MAS: 107; SHG: 271; KET: 28; SEH: 1; TOS: 300; MAK: 179
Cable cutter |  | pcs | 28 | 0 | SHG: 4; MAK: 24
Cable ties | Black cable ties | packets | 118 | 12 | MAT: 9; MAS: 16; SHG: 8; KET: 33; SEH: 11; TOS: 12; MAK: 16 | 1
Chain Block | 1.5ton | pcs | 312 | 0 | MAT: 12; MAS: 56; SHG: 66; KET: 101; SEH: 45; MAK: 32
Chisel | Flat cold chisel | pcs | 129 | 0 | MAS: 18; SHG: 66; SEH: 45
Circuit breaker | Circuit brteaker 63Amp | pcs | 880 | 360 | MAS: 280; SHG: 200; MAK: 40
Clevis Thimble | Clevis Thimble B30573 | pcs | 149 | 52 | MAT: 12; MAS: 23; SHG: 20; KET: 42
Coach Screw | Coach Screw | pcs | 1318 | 575 | MAS: 130; KET: 610; MAK: 2 | 1
Copper lug | M12*50mm | pcs | 38 | 15 | MAS: 8; SHG: 3; KET: 10; SEH: 2
Copper lug | M12*70mm | pcs | 300 | 0 | MAS: 200; KET: 60; SEH: 30; MAK: 10
Copper lug | M16*16mm | pcs | 100 | 46 | MAS: 30; KET: 20; SEH: 3 |  |  |  | 1
Curved Square Washers | M16 | pcs | 99 | 0 | MAT: 18; MAS: 24; SHG: 22; KET: 29; SEH: 6
D Shackle | 70kn | pcs | 221 | 60 | MAT: 14; MAS: 27; SHG: 28; RIB: 20; KET: 70; MAK: 2
Deadend | Deadend for fox | pcs | 681 | 14 | MAT: 200; SHG: 300; KET: 124; MAK: 43
Earth Rod | Earth Rod M12*1.2m | pcs | 242 | 225 | MAS: 2; SHG: 2; KET: 8; TOS: 2; MAK: 3
Earth Rod | Earth Rod M16*1.2m | pcs | 909 | 704 | MAT: 15; MAS: 15; SHG: 27; KET: 16; SEH: 12; MAK: 120
Earth Rod | Earth Rod 70/16 | pcs | 272 | 175 | MAS: 20; SHG: 10; KET: 52; SEH: 15
Earth Spike | Earth spike M16x1.5m | pcs | 986 | 792 | MAT: 50; TLH: 100; KET: 29; MAK: 8 |  | 7
Earth Spike | Earth spike M12x1.2m | pcs | 3861 | 3220 | MAT: 80; TLH: 6; MAS: 30; SHG: 120; KET: 44; SEH: 80; TOS: 160; MAK: 121
Earth Spike Clamp | 10pcs / box | pcs | 622 | 189 | MAT: 12; MAS: 12; KET: 30; SEH: 200; TOS: 160; MAK: 12 |  | 7
Earthing Kit | CER Earthing Kit | pcs | 413 | 404 | MAK: 9
End Cap | End GPE5END 25-95mm | pcs | 731 | 479 | MAT: 20; MAS: 62; SHG: 50; TOS: 50; MAK: 70
Eye Nut | M16 eye nut (LV) | pcs | 1496 | 1115 | MAT: 142; TLH: 4; MAS: 55; SHG: 17; KET: 63; MAK: 100
Eye Nut | M20 eye nut (MV) | pcs | 1203 | 983 | MAT: 45; MAS: 29; SHG: 15; KET: 109; MAK: 22
Fencing Staples (U nails) | 1kg | pkt | 34 | 6 | MAT: 3; TLH: 1; MAS: 3; KET: 5; SEH: 4; TOS: 7; MAK: 4 | 1
Ferrule Crimp | 10mm | pcs | 184 | 178 | KET: 6
Filament | PLA MODEL Filament | pcs | 825 | 0 | MAS: 400; SHG: 200; KET: 200; SEH: 25
Filament | ABS-GF25 Filament Model | pcs | 8 | 2 | MAS: 2; SHG: 2; MAK: 2
Fisher plug | 6 x 55 (100pcs/pack) | pcs | 2413 | 2297 | MAT: 8; KET: 6; TOS: 100; MAK: 2
Fuse Drop out | Dropout with fuse tube-porcelain 11-24kV 100A | pcs | 139 | 132 | MAT: 2; SHG: 1; KET: 2; MAK: 2
Fuse Links | 5Amps | pcs | 242 | 195 | MAT: 9; KET: 37; MAK: 1
Fuse Links | 10Amps | pcs | 41 | 20 | MAT: 4; KET: 9; MAK: 8
Galvanised Saddle | 20mm | pcs | 1525 | 69 | MAT: 200; SHG: 120; KET: 676; TOS: 200; MAK: 260
Galvanised Steel Conduit | 20mm | pcs | 429 | 68 | MAT: 80; MAS: 40; SHG: 84; KET: 116; TOS: 20; MAK: 21
Galvanised Steel Conduit | 32mm | pcs | 2 | 0 | TOS: 2
GP Earth Wire Green/Yellow | Cut 70mm | meters | 532 | 364 | MAT: 41; MAS: 15; KET: 97; MAK: 15
GP Earth Wire Green/Yellow | Cut 6mm | meters | 88 | 7 | MAT: 28; MAS: 17; KET: 10; MAK: 26
GP wire Green/Yellow | 16mm | meters | 276 | 263 | KET: 13
GP H/Wire Red | Cut 6mm | meters | 20000 | 16300 | MAT: 400; MAS: 1500; MAK: 1800
Hammer | 4 pounds hammer | pcs | 54 | 1 | MAS: 17; SHG: 21; SEH: 15
Heatshrink | 9.5 > 4.8mm | pcs | 33 | 28 | MAK: 5
Housewire | 6.0MM Black | meters | 13000 | 2200 | MAT: 4200; TLH: 100; MAS: 1600; SHG: 1500; KET: 2000; SEH: 100; TOS: 400; MAK: 800 | 100
Line Post Insulator | line Post Insulator 11kV, 7kN | pcs | 95 | 75 | TLH: 2; MAS: 3; SHG: 2; KET: 9; MAK: 4 |  |  |  |  | 8 of them were transferred to production
Link Stick | Link Stick | pcs | 84 | 1 | MAS: 21; SHG: 36; KET: 22; SEH: 4
Lug Crimp | Lug 16x16 mm | pcs | 314 | 280 | MAS: 24; MAK: 10
Lug Crimp | Lug 6mm x 6mm | pcs | 3334 | 3034 | SHG: 100; KET: 100; TOS: 100
Lug Crimp | 6mm x 8mm | pcs | 700 | 580 | SEH: 120
Lug Crimp | 10mm x 12mm | pcs | 8734 | 8534 | TOS: 200
Lug Crimp | 16mm x 12mm | pcs | 1562 | 1562
Lug Crimp | 16mm x 16mm | pcs | 166 | 66 | SHG: 100
L:ug Crimp | 240mm x 20mm | pcs | 2 | 0 | KET: 2
Lug Crimp | 70mm x 12mm | pcs | 1464 | 864 | MAT: 50; KET: 400; MAK: 150
Mosdofer Bracket | Mosdofer fuse holder Bracket 160A | pcs | 69 | 26 | MAT: 4; KET: 6; MAK: 33
Mosdofer Fuses | 160amps | pcs | 18 | 10 | KET: 5; MAK: 3
Mostofer Holder |  | pcs | 10 | 0 | KET: 10
Multifunction Crimping Tool |  | pcs | 84 | 72 | MAK: 6 |  |  |  | 6
Stay Rod non adjustable | Stay Rod MV | pcs | 50 | 0 | MAT: 8; KET: 42
Nuts | Nuts M20 | pcs | 986 | 903 | MAT: 23; MAS: 52; SHG: 2; KET: 6
Nuts | Nuts M16 | pcs | 166 | 166
Nuts | M8 | pcs | 20 | 0 | KET: 20
PG Clamp | PG Clamp 2BLT 16-120mm2 4-15 mm AL-AL | pcs | 187 | 0 | MAT: 29; MAS: 30; KET: 73; MAK: 55
Pigtail Bolt | M16 x 380mm | pcs | 2603 | 1793 | MAT: 102; MAS: 100; SHG: 254; KET: 75; SEH: 135; TOS: 100; MAK: 44
Pigtail Bolt | M12 x 340mm | pcs | 2442 | 1432 | MAT: 160; MAS: 141; SHG: 143; KET: 176; SEH: 160; TOS: 80; MAK: 144 | 6
Pigtail Screws | M8 X 150 MM | pcs | 3600 | 1314 | MAT: 17; MAS: 530; SHG: 1035; KET: 153; SEH: 400; TOS: 50; MAK: 101
Pin Insulator | 864mm | pcs | 121 | 7 | MAT: 12; MAS: 12; KET: 51; MAK: 39
Pole Top Make-Off | 7/3.35 (MV) | pcs | 2452 | 325 | MAT: 556; MAS: 400; SHG: 250; KET: 380; SEH: 500; MAK: 41
Pole Top Make-Off | 3/3.35 (LV) | pcs | 1493 | 888 | MAT: 112; MAS: 112; SHG: 79; RIB: 1; KET: 123; SEH: 40; TOS: 96; MAK: 41 |  |  |  | 1
Polymer Fuse cut out | 11kV | pcs | 202 | 0 | MAT: 1; MAS: 1; KET: 200
Pre-insulated Bi-metallic Lug | Pre-insulated Bi-metallic Lug 35mm | pcs | 350 | 22 | MAS: 131; SHG: 92; KET: 84; TOS: 8; MAK: 13
Pre-insulated Bi-metallic Lug | Pre-insulated Bi-metallic Lug 50mm | pcs | 128 | 128
Pre-insulated Bi-metallic Lug | Pre-insulated Bi-metallic Lug 70mm | pcs | 248 | 0 | MAT: 2; MAS: 64; SHG: 170; KET: 6; SEH: 3; MAK: 3
Preformed galv. steel guy grip | Preformed galv. steel guy grip (MV) 7*3.35 | pcs | 1679 | 943 | MAT: 143; MAS: 128; SHG: 250; KET: 190; MAK: 25
Preformed galv. steel guy grip | Preformed galv. steel guy grip (LV) 3*3.35 | pcs | 5244 | 3121 | MAT: 491; MAS: 311; SHG: 389; KET: 458; SEH: 120; TOS: 220; MAK: 134
Prop Bracket |  | pcs | 166 | -1 | MAS: 43; SHG: 39; KET: 54; SEH: 20; TOS: 1; MAK: 10
PVC Conduit | 20mm | pcs | 341 | 41 | 86 | 10 | 25 |  | ` | 25 | 93 | 25 | 18 |  | 18
PVC Conduit | 50mm | pcs | 49 | 3 | MAT: 36; SHG: 4; KET: 5; MAK: 1 |  |  |  |  | To be used on site and be returned to HQ.
PVC Conduit | 25mm | pcs | 273 | 7 | MAT: 45; MAS: 40; SHG: 70; KET: 75; SEH: 1; MAK: 35 |  |  |  |  | To be used on site and be returned to HQ.
PVC Coupling | 20mm | pcs | 764 | 764
PVC Coupling | 25mm | pcs | 70 | 70
PVC Glue | 200ml | pcs | 146 | 35 | MAS: 43; KET: 68
PVC Swa 4 core | 95mm | meters | 4 | 0 | KET: 4
Question mark bracket | Question mark bracket | pcs | 2200 | 2194 | MAT: 4; MAK: 2
Ratchet | Smaller one | meters | 8000 | 0 | MAT: 1500; MAS: 1500; SHG: 2000; LEB: 500; KET: 1000; TOS: 500; MAK: 1000
Scotch Eye Auger Bit | 16mm | pcs | 50 | 40 | MAK: 10
Scotch Eye Auger Bit | 22mm | pcs | 100 | 100
Silicon Long Rod Insulator | 11kV, 70kN | pcs | 671 | 1 | MAT: 138; MAS: 122; SHG: 115; KET: 97; MAK: 198
Silicon Long Rod Insulator | 22kV | pcs | 100 | 100
Single-phase Smart Electricity Meter | Single-phase DIN-rail 60 A AC | meters | 800 | 700 | MAS: 100
Sledge Hammer | 8 pounds Hammer | pcs | 4 | 4
Speed plug | 6mm*55mm | pcs | 4 | 4
Spindle | M20*250mm | pcs | 812 | 756 | MAT: 3; MAS: 3; KET: 50
Stay Insulator | (MV) | pcs | 35 | 35
Stay insulator (LV) | Stay Insulator 145mm LV | pcs | 117 | 0 | MAS: 33; SHG: 35; KET: 48; MAK: 1
Stay Insulator LV | Stay Insulator LV Porcelain 95L X 57W | pcs | 250 | 50 | MAS: 50; SEH: 50; TOS: 50; MAK: 50
Stay Insulator MV | Stay Insulator MV Porcelain | pcs | 77 | 0 | MAT: 40; MAS: 18; KET: 19
Stay Rod Adjustment | Stay Rod Adjustment M20 X 2400 | pcs | 307 | 307
Stay Thimble | Stay Thimble 16mm galvanised steel | pcs | 350 | 200 | MAT: 6; MAS: 17; SHG: 13; KET: 14; TOS: 100
Stay Wire (LV) | Stay wire 3/3.35 LV | meters | 3568 | 1700 | MAT: 610; MAS: 300; SHG: 358; KET: 500; TOS: 100
Stay Wire (MV) | (MV) | meters | 7500 | 7158 | MAT: 42; SHG: 100; KET: 200
Stay wire Galv | 7/3.35mm1100MPA1500M Drum+7x100m coils | meters | 261 | 261
Steel Nails | Flutted/ Steel Nails | pkt | 73 | 40 | MAT: 4; TLH: 1; MAS: 13; SHG: 2; KET: 2; SEH: 5; TOS: 4; MAK: 2
Steel Washers | M8 | Pkt | 5 | 5
Strain Insulated ABC | (LV) 35-70mm | pcs | 450 | 450
Surge Arrestor | 12kV (MV) 10kA | pcs | 92 | 75 | MAT: 3; MAS: 1; KET: 12; MAK: 1
surge Arrestor | 6kV (LV)10kA | pcs | 27 | 20 | MAT: 2; KET: 5
Suspension Clamp (LV) | (LV) | pcs | 535 | 101 | MAT: 29; MAS: 37; SHG: 153; KET: 146; TOS: 62; MAK: 4 | 3
T Pull | T Pull size 4 | pcs | 26 | 26
Thimblest Stay | Thimblest Stay 14mm wire | pcs | 48 | 48
Threaded Rod | M20 x 450 | pcs | 153 | 135 | KET: 17; MAK: 1
Threaded Rod | M20 by 600 | pcs | 48 | 46 | KET: 2
Threaded Rod | M20 by 350 | pcs | 26 | 21 | MAT: 2; MAK: 3
Threaded Rod | Threaded Rod M16 x 350 | pcs | 15 | 11 | KET: 1; MAK: 3
Threaded Rod | Threaded Rod M 20 x 250 | pcs | 216 | 63 | MAT: 75; KET: 73; MAK: 5
TTD | TTD 151 | pcs | 1001 | 358 | MAT: 124; TLH: 12; MAS: 80; SHG: 100; KET: 23; SEH: 200; TOS: 80; MAK: 24
TTD | TTD 201 | pcs | 883 | 85 | MAT: 100; MAS: 200; SHG: 150; KET: 228; SEH: 40; TOS: 80
Twin Ties for Fox |  | pcs | 220 | 158 | MAT: 10; KET: 14; MAK: 38
T Junction Box | T-junction box 20mm | pcs | 100 | -166 | MAT: 20; SHG: 80; TOS: 80; MAK: 86
Adaptors | Adaptors 25mm | pcs | 336 | 336 | [15 empty] | 20
Black wire | Black wire 35mm | Meters | 470 | 470
Nuts | M12 | pcs | 110 | 0 | MAT: 60; MAS: 50
Bulbs | bulbs | pcs | 20 | 0 | MAT: 20
Bundle wire | ABC/ Bundle wire | drum | 29 | 29
PVC Couplings | PVC Couplings 20mm | pcs | 100 | 100 | MAK: 50
Squirrel conductor | Squirrel conductor | Meters | 10000 | 0 | MAT: 3000; MAS: 2000; KET: 5000
Weasel conductor | Weasel conductor | meters | 14356 | 0 | KET: 14356
25KVA Single phase -oil immersed Transformer | 25KVA Single phase -oil immersed Transformer (stepdown) | pcs | 43 | 40 | KET: 3
75KVA Single phase -oil immersed Transformer | 75KVA Single phase -oil immersed Transformer (stepup) | pcs | 1 | 1
180KVA Single phase -oil immersed Transformer | 180KVA Single phase -oil immersed Transformer (stepup) | pcs | 1 | 0 | bar: KET
225KVA Single phase -oil immersed Transformer | 225KVA Single phase -oil immersed Transformer (step up) | pcs | 3 | 3
315KVA Single phase -oil immersed Transformer | 315KVA Single phase -oil immersed Transformer(step up) | pcs | 1 | 1
720KVA Single phase -oil immersed Transformer | 720KVA Single phase -oil immersed Transformer(step up) | pcs | 3 | 3
4 Core Wire 70mm | 4 Core Wire 70 mm | Meters | 20 | 20
GP H/Wire Red | 35 mm | meters | 258 | 258
CCS Grounding wire | CCS Grounding WIre 19 No5 | meters | 680 | 680
Airdac wire | 8mm CNE Airdac, sheath orange colour | meters | 19532 | 12468 | MAT: 1000; MAS: 3032; SEH: 500; MAK: 2532
Copper lug | M6-8mm | pcs | 400 | 0 | SEH: 200; MAK: 200
Ferrule Crimp | 1.5mm | pcs | 100 | 100
Copper lug | 35-8mm | pcs | 0 | 0
Fuse Links | 8Amps fuse link | pcs | 26 | 20 | KET: 6
DC Motorization | Slew Drive Motor (EM90ZYX06 Model) | pcs | 5 | 1 | [18 empty] | Mostly Used by OnM Team .First issue was on 26/01/2026 | bar: MAT; MAS; LEB; MAK
Iron Channel | 100*5*2.4m | pcs | 10 | 6 | KET: 4
Iron Channel | 76mm*38mm*750mm | pcs | 16 | 12 | KET: 4
Surge Arrester | Surge Arrester 24KV (HY10W-24L | pcs | 110 | 95 | KET: 15
Surge Arrester | (Neutral) 6kv | pcs | 4 | 0 | KET: 4
Bolt and nut | M6 Bolt and Nut | pcs | 500 | 200 | SEH: 100; TOS: 200
Earth Wire Cable | 16mm 1core Earth Wire Cable | meters | 250 | 250
Long Rod Insulator | 19-24kV 70KN C+T Silicone | pcs | 912 | 912
Transformer Lugs | Lugs for transformers cable supply | pcs | 564 | 564
Line Post Insulator | 19-24kV 10kN Capped EP477 Porcelain Brown | pcs | 756 | 756
Twin Ties for Squirrel | ATT-330 | pcs | 913 | 913
M16 Nuts | M16 Hex nuts | pcs | 5700 | 5440 | MAS: 100; SEH: 100; TOS: 60
M16 washers | M16 square washers | pcs | 1900 | 1680 | MAS: 100; SEH: 100; TOS: 20
Copper lug | 25-10mm | pcs | 0 | 0
Copper lug | 36-16mm | pcs | 0 | 0
Copper lug | 70-10mm | pcs | 11 | 11
Copper lug | 16-6mm | pcs | 5 | 5
Copper lug | 16-16mm | pcs | 75 | 35 | KET: 40
Copper lug | 50-10mm | pcs | 9 | 9
Copper lug | 6-6mm | pcs | 39 | 39
Mosdofer Fuses | 63AMP | pcs | 8 | 0 | KET: 8
Bare Copper Wire | Cut 25mm Bare Copper Earth Wire (0.22) | meters | 100 | 100
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Copper lug | 25-10mm | pcs | 0 | 0
Copper lug | 36-16mm | pcs | 0 | 0
Copper lug | 70-10mm | pcs | 11 | 11
Copper lug | 16-6mm | pcs | 5 | 5
Copper lug | 16-16mm | pcs | 75 | 35 | KET: 40
Copper lug | 50-10mm | pcs | 9 | 9
Copper lug | 6-6mm | pcs | 39 | 39
Mosdofer Fuses | 63AMP | pcs | 8 | 0 | KET: 8

## RET items request log
0 | Email Address | Full Names of Requester | Items Requested | Concession/Site | Estimated Time of Dispatch to Site | Name of Assigned Receiver on Site | Email of Assigned Receiver on Site | notes | database_updated
2023-11-06 16:02 | jopi@1pwrafrica.com | Leoma Jopi | 4pounds hummer(1) 8pounds hummer(1) Chisels(2) | SEH | 2023-11-06 | Leoma Jopi | jopi@1pwrafrica.com | all requested items given | yes
2023-11-07 07:20 | komete@1pwrafrica.com | Mokhethi Komete | 4 pounds hammers (3) Pvc conduits 20mm (25) Pvc conduits 25mm (10) Steel conduits 20mm (25) Insulated copper conductor 6mm (100m) | TLH | 2023-11-07 | Mokhethi Komete | komete@1pwrafrica.com |  | yes
2023-11-07 08:24 | seshemane@1pwrafrica.com | Lefa seshemane | Buckles (200),binding strap (2), strain clamp(12) Lv stay rods (5) | MAS | 2023-11-06 | Seshemane | seshemane@1pwrafrica.com |  | yes
2023-11-07 08:45 | monaheng@1pwrafrica.com | Rethabile Monaheng | 4 pounds=1 Flat Chisel=2 | TOS | 2023-11-07 | Monaheng | monaheng@1pwrafrica.com | all requested items given | yes
2023-11-07 08:45 | ramothule@1pwrafrica.com | Motiki Ramothule | 4 pounds=2 Chisel flat=2 | SEB | 2023-11-07 | Motiki Ramothule | ramothule@1pwrafrica.com | all requested items given | yes
2023-11-07 08:47 | kalake@1pwrafrica.com | Tebello kalake | 4pounds hummer=2 Plat chiesel=1 Crimping tool=1 Chain block 1.5ton =1 | SHG | 2023-11-07 | Tebello kalake | kalake@1pwrafrica.com | all requested items given | yes
2023-11-07 09:00 | seshemane@1pwrafrica.com | Lefa Seshemane | Chesel & 8 pounds | MAS | 2023-11-06 | Lefa Seshemane | seshemane@1pwrafrica.com | all requested items given | yes
2023-11-07 09:02 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | 8 pound=1, 4 pounds=2,chiesel=2 | MAT | 2023-11-07 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com |  | yes
2023-11-07 09:07 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | 4 pounds hammer=4, Chisels=2, cable cutter=1, Bolt cutter=1 | KET | 2023-11-07 | Tiisetso Mahlehla | mahlela@1pwrafrica.com | all requested items given | yes
2023-11-07 09:25 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | 1 cable cutter | MAT | 2023-11-07 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-11-07 13:01 | komete@1pwrafrica.com | Mokhethi Komete | Chisels (2) | TLH | 2023-11-07 | Mokhethi Komete | komete@1pwrafrica.com | all requested items given | yes
2023-11-14 07:44 | letseka@1pwrafrica.com | Taole Letseka | Small generator for park home lighting | SEH | 2023-11-15 | Taole Letseka | letseka@1pwrafrica.com | not yet given | no
2023-11-15 11:34 | lempe@1pwrafrica.com | Rethabile Lempe | Meters (4), Single channel enclosure (2), LV Stainers (8), m16 threaded rod (3), m16 eye nut (3), Earth spikes 1.2m (3), 20mm*6m Conduit (3), Suspension clamps (5), Neutral wire 6mm*30m (1) | MAK | 2023-11-15 | Rasekeiti Mohlomi | rasekeiti@1pwrafrica.com | all requested items given | yes
2023-11-17 07:54 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | 10 normal globes(60w) | MAT | 2023-11-17 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-11-17 15:20 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Cable ties 2 packets | MAT | 2023-11-17 | Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-11-17 15:43 | komete@1pwrafrica.com | Mokhethi Komete | Insulated copper conductor 6mm (100m) 60W globes (15) | TLH | 2023-11-18 | Mokhethi Komete | komete@1pwrafrica.com | material not in store
2023-12-04 09:19 | lichaba@1pwrafrica.com | Lichaba West | 1 generator battery | TLH | 2023-12-06 | Lichaba West? | lichaba@1pwrafrica.com | all requested items given | yes
2023-12-04 09:20 | makhoalinyane@1pwrafrica.com | Makhoalinyane Teboho | Surge arrestor 12kv *2, surge arrestor 6kv*1,fuse link 5A *4 | MAT | 2023-12-04 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-12-04 09:22 | makhoalinyane@1pwrafrica.com | Makhoalinyane Teboho | Step down transformer | MAT | 2023-12-04 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-12-04 11:03 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac Strainers 20 and cable ties 2 packets | MAT | 2023-12-04 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-12-09 12:33 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac 500m,6mm black cable, earth spikes 1.5m | MAT | 2023-12-09 | Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested items given | yes
2023-12-24 08:41 | lempe@1pwrafrica.com | Rethabile Lempe | Uninterruptable Power Supply (UPS) | MAT | 2023-12-24 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2024-01-04 14:24 | letseka@1pwrafrica.com | Taole Letseka | Cut-off assembly and 5A fuse | MAK | 2023-12-31 | Taole Letseka | letseka@1pwrafrica.com
2024-01-04 16:46 | serobanyane@1pwrafrica.com | Neo Serobanyane | Readyboard (1), 6mm earth wire (10m), TTD 151 (4), buckles (10), eye nut (1), ABC strainer (1) | MAK | 2024-01-05 | Neo Serobanyane | serobanyane@1pwrafrica.com | all requested items given except ABC Strainer | yes
2024-01-12 09:23 | lempe@1pwrafrica.com | Rethabile Lempe | TTD (151 * 2) for MAK line maintenance | MAK | 2024-01-12 | Komete | komete@1pwrafrica.com | only 1 found in stock | yes
2024-01-19 15:53 | eng-team@1pwrafrica.com | Kananelo Shale | Earthing Rod 1.6m(1), Earth clamp (1) | HQ | 2024-01-19 | Kananelo Shale | kananelo@1pwrafrica.com | all requested items given | yes
2024-01-22 11:23 | mpapea@1pwrafrica.com | Jame mpapea | TTD 151 for repairing Lv termination at MAK (6) | MAK | 2024-01-22 | Rethabile lemphe | rethabile@1pwrafrica.com | all requested items given | yes
2024-01-23 10:37 | lichaba@1pwrafrica.com | Lichaba West | 2, 20mm conduit pipes | HQ | 2024-01-23 | Lichaba West | lichaba@1pwrafrica.com | all requested items given | yes
2024-01-23 11:30 | lichaba@1pwrafrica.com | Lichaba West | 3 dryness batteries | HQ | 2024-01-23 | Lichaba West | lichaba@1pwrafrica.com | all requested items given | yes
2024-01-24 10:54 | lichaba@1pwrafrica.com | Lichaba West | Window for TLH worker camp | TLH | 2024-01-29 | Lichaba West | lichaba@1pwrafrica.com | all requested items given | yes
2024-01-29 17:03 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Longrods(12),Guy grip MV(12),eye nuds M20(12), 250mm(8), dead end 14,stay thimble 18,stay wire MV(50m). | MAT | 2024-01-30 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested items given | yes
2024-01-30 10:30 | lichaba@1pwrafrica.com | Lichaba West | 1 nut for TLH TCU | TLH | 2024-01-30 | Lichaba West | lichaba@1pwrafrica.com | all requested items given | no
2024-02-08 15:02 | eng-team@1pwrafrica.com | Kananelo Mokobori | 20mm PVC conduit pipe (1) | HQ | 2024-02-05 | Kananelo Mokobori | kananelo@1pwrafrica.com | all requested items given | yes
2024-02-14 08:42 | serobanyane@1pwrafrica.com | Neo Serobanyane | Guy grip (3), Thimble (2), M20x250 threaded bolt (1), M20 Eye nut (1), Stay wire (7m) | MAK | 2024-02-14 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-02-14 08:54 | seshemane@1pwrafrica.com | Lefa Seshemane | Spark meters (10) Single Channel Enclosures (10) U-nails (2kg) Bandit strap (2) pig tails M12 (30) T Junction (30) Steel conduit (15) ABC Strainers (30) Earth Spikes 1.5m (14) 6mm House wire 80m Fisher plugs (1 box) Buckles (60) Thimble (12) 20mm Steel saddles (130) steel nails | MAS | 2024-02-14 | Lefa Seshemane | seshemane@1pwrafrica.com | all requested items given except meters | yes
2024-02-23 09:17 | lichaba@1pwrafrica.com | Lichaba West | LV stay wire (40m) | SEH | 2024-02-24 | Lichaba West | lichabajameswest@gmail.com | all requested items given | yes
2024-02-23 17:17 | lichaba@1pwrafrica.com | Lichaba West | 20mm pvc conduit 4m x 3 20mm pvc couplers x 10 240 x 12mm lugs x 20 earth spike clamps x3 line taps 35mm x2 | SEH | 2024-02-24 | Lichaba West | lichaba@1pwrafrica.com | all available items given | yes
2024-02-26 10:30 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Stay wire(2 rolls), stay rods(15),stay plates(15), stay insulators(15), stay thimble(15), pole top(15), gay grip(45), eyenut(18), bundle strainers(10), Bundle suspension(7), end cap(15), airdac(1roll), pvc conduit 20mm(5), Fisher plug(25), saddle galvanised 20mm(4), steel conduit 20mm(4), stainless steel strapping(2packets), strapping buckles(30) | SEH | 2024-02-25 | Tiisetso Mahlehla | mahlela@1pwrafrica.com | all requested items given | yes
2024-02-26 10:33 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Stay rod(10), stay plate(10),bare wire/copper wire (1 roll) | MAS | 2024-02-24 | Lefa Seshemane | seshemane@1pwrafrica.com | all requested items given | yes
2024-02-26 10:45 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Readyboards (6) 2 channel enclosures (4) 3 channel enclosures (2) | SEH | 2024-02-24 | Tiisetso Mahlehla | mahlela@1pwrafrica.com | all requested items given | yes
2024-03-08 15:20 | teboho@1pwrafrica.com | Teboho Noko | Bundle strainers=10 Bundle Suspension=5 3 way pole box =1 Readyboards=4 Stay wire 1 roll(100m) | SEH | 2024-03-08 | Mahlehla | mahlehla@1pwrafrica.com | all requested items given
Yes | serobanyane@1pwrafrica.com | Neo Serobanyane | Airdac (40m), Earthwire (10m), 20mm conduit (4m), 25mm conduit (4m), 16mm pigtale (1), Earth spike (1) | MAK | 2024-03-14 | Neo Serobanyane | serobanyane@1pwrafrica.com | all requested items given | yes
2024-03-15 12:37 | serobanyane@1pwrafrica.com | Neo Serobanyane | M20 Eye Nut (2), M20 Threaded rod (2), Thimble (2) | MAK | 2024-03-18 | Neo Serobanyane | serobanyane@1pwrafrica.com | all requested items given | yes
2024-03-19 14:44 | maks@1pwrafrica.com | Makoanyane | 3 x 50mm pvc pipe 4 x 50mm pvc elbows 3 x 20mm pvc pipe 100m stay wire 2 x 4m x 20mm steel pipe 10 x I-nut | KET | 2024-03-20 | Makoanyane | maks@1pwrafrica.com | all requested items given | yes
2024-03-20 09:37 | maks@1pwrafrica.com | Makoanyane Khakanyo | 15m air dec | KET | 2024-03-20 | Neo Makosholo | neo@1pwrafrica.com | all requested items given | yes
2024-03-20 10:36 | maks@1pwrafrica.com | Makoanyane Khakanyo | 12 lipped crossarms | KET | 2024-03-20 | Makoanyane Khakanyo | maks@1pwrafrica.com | all requested items given
2024-03-21 08:00 | maks@1pwrafrica.com | Makoanyane Khakanyo | 10KVA genset, 80m x 25mm bare earth wire. | KET | 2024-03-21 | Neo Makosholo | neo@1pwrafrica.com | all requested items given
2024-03-21 10:08 | letseka@1pwrafrica.com | Taole Letseka | U-nails by 2kg, 100m stay wire, binding wire | MAK | 2024-03-21 | Taole Letseka | letseka@1pwrafrica.com | all requested items given
2024-04-09 07:13 | monoane@1pwrafrica.com | Sello Monoane | 1 genset, 1 drill, micro blasting kit | MAK | 2024-04-09 | Sello Monoane | monoane@1pwrafrica.com | all requested items given
2024-04-10 10:32 | komete@1pwrafrica.com | Mokhethi Komete | Pvc conduits 25 mm ×2 Pvc conduits 20 mm ×5 Earth spikes 1.5 m ×5 | TLH | 2024-04-10 | Mokhethi Komete | komete@1pwrafrica.com | all requested items given | yes
2024-05-08 08:53 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac, airdac Strainers* 2, pick tails *2,fisher plugs, conduit 20mm*6m,conduit 25mm*1m,earth spike +lugs 1.5*1, black house wire 6mm*10m,guider bolt 6mm *1 | MAK | 2024-05-08 | Makhoalinyane | makhoalinyane@1pwrafrica.com
2024-05-16 09:02 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Spare meter, spare breaker, wires, furrels, airdac 20m, airdac Strainers | MAK | 2024-05-16 | Makhoalinyane | makhoalinyane@1pwrafrica.com
2024-05-20 12:37 | kalake@1pwrafrica.com | Tebello kalake | For Procurement Item Specification Qty. Per Unit Step Up 0 step down 0 Combi Unit Set 0 Dropout w/ Fuse Tube (Dropout SET) 0 Question Mark Bracket (Dropout) 0 Dropout Fuse - 5A 0 Dropout Fuse - 10A 0 Solid links 2 Surge Arrestor - 12kV (MV) 0 surge arrestors(6kv) 0 Bi-metalic lugs 0 Copper Lug(???mm) 0 Copper lugs 70mm 0 16mmx12mm lug 12 Wire Lug - 10*12 72 Wire Lug - 6x6 60 Pre-insulated lugs-35mm 0 Pre-insulated lugs-70mm 0 Bolt and nut 6x20 30 PG Clamp 12 Earth Spike Clamp 0 Earth Spike - 1.2m 75 Earth Spike - M16x1.5 0 FOX 1920 m Wire - ABC - 1-Phase (35mm) 750 m Wire - AIRDAC - 10mm - CNE 2300 m Wire - Earth - BCEW - 70mm (HEE) 0 m Wire - House - 70mm - Green/Yellow (HEE) 0 m 16mm green/yellow 12 m Wire - House - 06mm - Black (HEE) 550 m Earth Wire (stay wire) 92.05 m Conduit Steel -20mm 16.2 Conduit PVC - 25mm 12 Conduit PVC - 20mm 30 Stock - Plastic - PVC - Pipe - 50mm 0.75 Conduit - 20mm - T-Piece 40 Conduit - 20mm - Coupling 0 Saddle - Galvanized - 20mm (HEE) 180 Cable Tie - 200mm 600 Pitail Bolt and Nut Assembly M12 Pigtail Screw M12 30 Pigtail Bolt - M16 30 Eye Nut - M16 6 Eye Nut - M20 14 Hardware - Screw - Anchor - Nail-In - 06x055 5 steel nail 30mmx2.8mm 500 TTD Connectors 151 130 TTD Connectors 201 170 Airdac-10mm strainers 130 Airdac suspension clamp 30 Strain Clamp - Large (ABC) 22 Suspension Clamp 4 Ready Board (HEE) 45 Cement 200 Kg End Cap 33 Long Rod Insulator 14 Pin Insulators/Line Post Insulator 4 Thimble Clevis - 70kN (MV) 14 D-Shackle - 70kN 14 Spindle - M20 6 Twin Ties - Fox 12 Dead End - Fox 14 Strapping 36 Strapping Buckle 72 U Nail (HEE) 202.1 steel nail 30mmx2.8mm 200 Hardware - Screw - Coach 6 Threaded Rod Assembly - M20x450 1 Threaded Rod Assembly - M20x250 12 Threaded Rod Assembly - M20x350 0 Flat Bracing Strap - 910x50x6 2 Pole - Cross-Arm - 2.5m 0 Transformer Channels( Small) 0 Transformer Channels( Big) 0 Stay Rod Base Plate (LV) 15 Stay Rod (LV) 15 Stay Insulator - 90mm (LV) 15 Stay Thimble 15 Wire - Stay - 3x3.35 (LV) 105 m Guy Grip - 3x3.35 (LV) 45 Pole Top Make-Off - 3x3.35 (LV) 15 Stay Rod Base Plate (MV) 6 Stay Rod (MV) 6 Wire - Stay - 7x3.35 (MV) (HEE) 60 m Stay Insulator - 145mm (MV) 6 Guy Grip - 7x3.35 (MV) 18 Pole Top Make-Off - 7x3.35 (MV) 6 globes 15 | SHG | 2024-05-21 | Tebello kalake | kalake@1pwrafrica.com
2024-05-24 10:09 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Lv stay rod=6, lv stay plate=6,thimbles=6,stay wire=100m,lv gay grip=18,lv pole tops=6,pigtails=10,M16 eye nut=3,strainers=6,suspension=5,cable ties=100,TTD 201=8,Unails=23,ABC bundle=1000m,end caps=9,50mmpvc conduit=4m,20mm pvc conduit=2,steel nails=60,6mm black wire=100m,airdac 50m,buckles=20,20mm saddles=12,M12 pig tail=1, bolt and nut=1,6mm lug=1,16mm lugs=3,airdag strainers=2,20mm steel pipe=1,1.2 earth spike=2,strap bundit=100m,TTD 151=4,chain block 0.75t=1,grimping tool=1,cable cutter=1,running wheel=2,lugs 70 by 12=2, mv stay rod=1,mv stay plate=1,pick 3 way junction box=1 | KET | 2024-05-24 | Tiisetso Mahlehla | tiisetsomahlehla@gmail.com
2024-05-30 07:59 | monoane@1pwrafrica.com | Sello Monoane | Crowbars (3) | MAK | 2024-05-30 | Sello Monoane | monoane@1pwrafrica.com
2024-06-17 17:42 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Single channel *1 spare meter, airdac 50m | MAK | 2024-06-18 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2024-06-18 11:00 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | 63A breaker, 20mm conduit pipe, saddles, lugs 10*12 *2 | MAK | 2024-06-18 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | all requested given
2024-07-08 15:14 | kalake@1pwrafrica.com | Tebello kalake | 20mm pvc conduit (35) 20mm pvc T junction (30) 50mm pvc conduit (1) D-shackle (20) 20mm steel pipe (15) 1.5m earth spikes (20) Earth resistance tester (1) Earth kid (1) M20 × 350mm threaded rods (3) Rock drill (1) Rock drill bits (2) Link stick (1) | SHG | 2024-07-09 | Tebello kalake | Kalake@1pwrafrica.com
2024-08-13 15:37 | kalake@1pwrafrica.com | Tebello kalake | Airdac (drum) Steel pipes (20) Bold and nuts 6mm (30) 6mm lungs(30) | SHG | 2024-08-14 | Tebello kalake | Kalake@1pwrafrica.com
2024-08-14 11:22 | kalake@1pwrafrica.com | Tebello kalake | M16 pig tail(2) Lv guy grip(17) Lv stay rods(14) Lv stay plates(14) Lv stay insulator(10) Mv stay rods(2) Mv stay plates (2) Mv guy grip (6) M12 pig tails(10) Mv dead ends(20) Mv pin insulator(6) Mv spindle(6) Mv stay wire(roll) | SHG | 2024-08-15 | Tebello kalake | kalake@1pwrafrica.com
2024-08-14 16:47 | seshemane@1pwrafrica.com | Lefa seshemane | Thimble clevis=6 D shackles=14 Green & yellow earth= 2m | MAS | 2024-08-15 | Lefa seshemane | seshemane@1pwrafrica.com
2024-08-19 16:01 | seshemane@1pwrafrica.com | Seshemane Lefa | Pig tail M16 | SHG | 2024-08-20 | Seshemane Lefa | seshemane@1pwrafrica.com
2024-08-20 10:12 | seshemane@1pwrafrica.com | Seshemane Lefa | Eye nut M16=13 , Steel saddle = 200( 2 pcts) | SHG | 2024-08-21 | Seshemane Lefa | Seshemane@1pwrafrica.com
2024-09-09 12:58 | rethabile@1pwrafrica.com | Rethabile Lebajoa | Rock drill and bits | TOS | 2024-09-27 | Rethabile Lebajoa | rethabile@1pwrafrica.com
2024-09-09 16:28 | seshemane@1pwrafrica.com | Seshemane Lefa | Airdac 500m | SHG | 2024-09-10 | Seshemane Lefa | seshemane@1pwrafrica.com
2024-09-10 08:40 | monoane@1pwrafrica.com | Sello Monoane | M20 & M16 wood drill bits | MAT | 2024-09-11 | Molupe Foso | foso@1pwrafrica.com
2024-09-10 09:21 | seshemane@1pwrafrica.com | SESHEMANE LEFA | Earth spike 10, Transformer 1,threated rods 250mm 8,drop out bracket 2 | MAS | 2024-09-11 | Seshemane Lefa | seshemane@1pwrafrica.com
2024-09-11 14:41 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Cable ties*1, 12mm pick tails | TLH | 2024-09-12 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2024-09-18 10:33 | monoane@1pwrafrica.com | Sello Monoane | 1 crowbar, 4 chisels and 4 Hammers. | MAK | 2024-09-18 | Mokhethi Komete | komete@1pwrafrica.com
2024-09-20 10:10 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Spare alternator from 100kva generator for MAK | MAK | 2024-09-20 | Makhoalilinane | makhoalinyane@1pwrafrica.com
2024-10-08 11:05 | petlane@1pwrafrica.com | Petlane | Stay rod 7/3.35 (4) Stay plate 7/3.35 (4) Stay Insulator 7/3.35 (4) Pole top make off 7/3.35 (10) Coach screw (6) Guy grip 7/3.35 (12) Stay wire 7/3.35 (100m) U nails ( 1 packet) Stay wire 3/3.35 (200m) ABC strain clamp (11) TTD 25-95 (21) Stay plate 3/3.35 (3) Stay rod 3/3.35 (3) Pole top 3/3.35 (3) Cable ties T120s (200) | KET | 2024-10-09 | Petlane Lekau | petlane@1pwrafrica.com
2024-10-08 11:31 | petlane@1pwrafrica.com | Petlane Lekau | 4 pounds hammer (2) Chisels (3) | KET | 2024-10-09 | Petlane | petlane@1pwrafrica.com
2024-10-08 12:50 | kalake@1pwrafrica.com | Tebello kalake | 20mm steel pipes (15) 20mm coduit pipes (30) Steel saddles box (137) Airdac strains (60) ABC strains (10) Steel nails (0.5kg) Cable ties (800) | SHG | 2024-10-08 | Tebello kalake | kalake@1pwrafrica.com
2024-10-11 14:22 | mpapea@1pwrafrica.com | James mpapea | Blackwire 6mm*2 | MAS | 2024-10-14 | Tebello kalake | kaleke@1pwrafrica.com
2024-10-31 09:40 | serobanyane@1pwrafrica.com | Neo Serobanyane | ABC bundle (58m), Guy grip (3), LV pole top (1), LV stay insulator (1), LV stay wire (30m), stay plate (1), 6mm black wire (10m), 20mm PVC conduit (4m), 20mm steel saddle (4), M12 pigtale (1), M20 eye nut (2), 1.2m earth spike (4), LV airdac strainer (3), ABC bundle strainer (5), 10x12mm lug (2) | MAK | 2024-10-30 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-10-31 10:22 | serobanyane@1pwrafrica.com | Neo Serobanyane | ABC bundle (110m), M20 eye nut (2), 70mm self tapping screws (10), Airdac (30), binding strap (box), 20mm steel saddle (10), generator (1), 16mm earth wire (7m), 20mm galvanized steel pipe (4m), thimble (2), 20mm boro (1), chain block (1), pole climbing shoes (1) | MAK | 2024-10-31 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-11-06 12:15 | seshemane@1pwrafrica.com | LEFA SESHEMANE | Long Rods=28,D shackles=28 Pig tail M16=48 Question Mark=2 Mustofor bracket=2 M12 pig tail=17 Clevis=28 Mv stay insulator 4 House wire 6mm 100m Mv stay 100m Cable ties 5p Unail 2KG Strain clamp ABC 28 Stay rods=24 Pg clamp=20 Guy grip=30 Threated rods 650mm=2 Twin tie=4 Pole top lv =30 Pole top mv 10 | MAT | 2024-11-07 | Lefa seshemane | seshemane@1pwrafrica.com
2024-11-06 17:14 | lekhelebane@1pwrafrica.com | RANTSO LEKHELEBANE | Mv stay wire*100m Pigtails M16 × 106 Dead-end *17 Bandit strap* 300m Stay plates LV *58 Stay plates MV*15 ABC Strain Clamps * Threaded rods 250mm*22 Airdac strain clamps*188 Guy grip LV*174 PVC Glue*1 Pigtails M12*94 Twin ties(fox)*11 Threade rods 450mm*3 End caps*85 Buckles *200 Thimble*58 PG Clamps*35 TTD 201*77 T junction 20mm × 94 Pole tops MV*15 Pole tops LV*58 Cable ties 360*1112 Couplings 20mm*94 House wire 6mm* Thimble clevis*17 D shackles *17 Long rods *17 Saddles 20mm*827 U nails *1355 Suspension clamps*31 Wire lugs 16*16mm* Wire lugs 06*8mm Eye nut M16* Eye nut M20*17 Pin Insulator*15 Guy grip MV*45 Ready board*17 Mosdorfer Bracket*3 Mosdorfer fuse holder*8 Fuse 160A*8 Neutral arrest *3 Earth spike clamp*42 Spindle*1 Curved square washer*22 Line post insulator*11 Drop out*5 Earth spike 1.5*10 Green n yellow 70mm*30m Drop outfuse*5 Pre insulated lugs 35*15 Pre insulation lugs 50*8 ? Mark bracket*5 ABC conductor 35*1 *1000m Conduit 20mm*200 | MAS | 2024-11-06 | Rantso Lekhelebane | lekhelebane@1pwrafrica.com
2024-11-07 09:23 | serobanyane@1pwrafrica.com | Neo Serobanyane | 35mmx8mm lugs (8), 35mm 4 core cable (30m), hydraulic crimping tool (1) | MAS | 2024-11-06 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-11-07 09:27 | serobanyane@1pwrafrica.com | Neo Serobanyane | LV guy grip (6), LV Isolator (2), stay rod (2), base plate (1) | MAK | 2024-11-06 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-11-07 10:18 | lekhelebane@1pwrafrica.com | Rantso Lekhelebane | Stay rod 20 are taken by Tos team from Mashai ret items..... | MAS | 2024-11-07 | Rantso Lekhelebane | lekhelebane@1pwrafrica.com
2024-11-08 09:54 | serobanyane@1pwrafrica.com | Neo Serobanyane | Airdac (30m), 201 TTD (8), M20 pigtail (6), LV pole top (4), generator (1), 1 way junction box (10), steel nail (30), 20mm PVC conduit (12m) | MAK | 2024-11-08 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-11-11 15:02 | serobanyane@1pwrafrica.com | Neo Serobanyane | 12kv surge arrestor (1), steel nail (packet) | MAK | 2024-11-11 | Neo Serobanyane | serobanyane@1pwrafrica.com
2024-11-13 09:32 | rethabile@1pwrafrica.com | Rethabile lebajoa | Bundle conductor (1000m) Pigtail m12 (60) Airdec (500m) Strainer clamps (54) Steel pipe 20mm (20) Pvc conduit pipe 25mm (6) TTD 201 (20) Pole box single channel (10) 3channel (6) 2channel (5) | KET | 2024-11-13 | Motiki Ramothule | ramothule@1pwafrica.com
2024-11-19 07:49 | seshemane@1pwrafrica.com | Lefa seshemane | Fox 3000m ,bundle 1000m & airdac 1000m | MAS | 2024-11-19 | Tiisetso Mahlehla | mahlehla@1pwrafrica.com
2024-11-19 07:52 | seshemane@1pwrafrica.com | Lefa seshemane | Fox 3000m & bundle 1000m | MAK | 2024-11-19 | Tebello Kalake | mahlehla@1pwrafrica.com
2024-11-19 13:12 | mpapea@1pwrafrica.com | Jsmes mpapea | Pvc confuit pipe 20mmx4m 24 Brazing dtrsp 6 Stay plate. 7/3.35 7 Stay rod. 7/3.35 7 Pin insulators 7/3.35 7 Pin insulators 3/3.35 29 Long rods. 10 Threaded rod 250mm Question mark brackets 4 Mosdofer brackets 6 Binding seal 10 Pig tail M16 60 Pig tail M12 8 Metal lugs x 70mm 18 Pg clamps 15 Square washer 20 Steel saddle 20mm 600 M20 nut 20 End cap 42 Fisher placks(8) 200 1.2m earthspike 6 Guy grip 4/3.35 91 Mosdofer fuse 5A 6 Dropout 4 Clevis thimble 10 D-dhackle 10 M20 eye nut 20 M16 eye nut 56 Dead end for fox 20 Guy grip 7/3.35 21 Twin ties for fox 32 Stay rod 3/3.35 33 Stay plate 3/3.35 29 6mm black wire 500m Pole top make off 3/3.35 30 Pole top make off 7/3.35 8 1.5m earthspike 50 Cable ties 600 TTD 151 200 TTD 201 30 Fisher placks(6) 330 Buckles 200 Pre-insulated lugs 70mm 5 Pre insulated lugs 35mm 10 Coach screw 36 Pvc T-junction box 20mm 68 U nails 8 packets Stay thimble 29 ABC suspension 16 10A fuse 4 | KET | 2024-11-06 | Petlane Lekau | petlane@1pwrafrica.com
2024-11-22 18:20 | seshemane@1pwrafrica.com | Lefa Seshemane | Guy grip (lv) 15,Bundle 1000m,Fox 1000m,Long Rods 12,D shackles =12,Thimble clevis =12, Pig tail M16=20,airdac strain=36,Pin insulator =12,Dead End=20,wire cable 6mm=100m, Lv stay wire 200m | MAT | 2024-11-21 | MOLUPE FOSO | foso@1pwrafrica.com
2024-11-26 17:52 | kalake@1pwrafrica.com | Tebello Kalake | Lv stay rods(20) Lv stay plate(17) Lv stay wire (1 roll) | MAK | 2024-11-11 | Tebello kalake | kalake@1pwrafrica.com
2024-11-29 08:12 | kalake@1pwrafrica.com | Tebello kalake | Twin ties (18) Long rods(26) M20 eye nuts (30) M16 eye nuts (20) Lv stay wire (100)m Cable ties (300) Vimble clevis (30) D shackle (30) Lv train clamp (50) Lv suspension (15) Unails (3kg) M20*250mm (30) M20*450mm(1) Mv stay insulator (10) Lv stay insulator(12) PG clamps (20) Mv pole top (2) Lv pole top(9) Stay vimble(23) Lv stay plate(1) Mv stay rods (5) Mv stay plate (5) Mv guy grip(40) Lv guy grip(41) Prop bracket(3) Dead ends(40) Braising strap(2) Pin insulator(10) | MAK | 2024-11-22 | Tebello kalake | kalake@1pwrafrica.com
2024-12-03 07:36 | komete@1pwrafrica.com | Mokhethi Komete | 1.2 earthspike (20) | MAS | 2024-12-03 | Mokhethi Komete | komete@1pwrafrica.com
2024-12-12 05:39 | foso@1pwrafrica.com | Molupe Foso | Drum of Airdec (1) | MAT | 2024-12-12 | Molupe Foso | foso@1pwrafrica.com
2025-01-14 08:24 | komete@1pwrafrica.com | Mokhethi Komete | LV stay rods 8 ABC strainers 40 6mm conductor 300M M16 pig tail bolts 60 1.2 Earth spikes 20 Airdac cable 2 drums (1000M) | MAS | 2025-01-14 | Mokhethi Komete | komete@1pwrafrica.com
2025-01-14 11:37 | komete@1pwrafrica.com | Mokhethi Komete | Pick axe | MAS | 2025-01-14 | Mokhethi Komete | komete@1pwrafrica.com
2025-01-23 14:53 | kalake@1pwrafrica.com | Tebello kalake | Pigtails(40) Straps(4) Abc strainers(35) Mv stay plates(10) Cross arms(3) | MAK | 2025-01-14 | Tebello kalake | kalake@1pwrafrica.com
2025-02-17 16:12 | rethabile@1pwrafrica.com | Rethabile lebajoa | Airdec 500m Pvc condiuts 24 Steel pipe 20mm 15 Black wire 6mm *2 TTD 201 50 | KET | 2025-02-18 | Petlane | petlane@1pwrafrica.com
2025-02-18 18:07 | ralekaota@1pwrafrica.com | Lebohang Ralekaota | Surge arrestors 12kv×2,bare earth wire 70mm×30m,1packet saddles, 1packet steel nails,1 packet u nails,ready boards×15 | MAT | 2025-02-05 | Lebohang Ralekaota | ralekaota@1pwrafrica.com
2025-02-18 20:51 | kalake@1pwrafrica.com | Tebello kalake | Spindle(26) Cable ties(3 packers) Eye nuts m16(30) Bandit strap(5 boxes) Bolt nut m6 ×25mm(60) Lugs 70 by 12mm(10) Earth spike clamp (6) Drop out(2) Treathed rod M20 x 450mm (3) Stay insulator lv (12) Airdac strainers (64) Stay wire MV (100m) Abc suspension(15) Preinsulated lugs 70mm(10) Pre insulated lug 35mm(10) TTD 201 (150) Drop out brakets (2) Mostofer holder(3) Fisher plugs (3 boxes) Mostoffer fuse(3) Fuse link 5 Am (3) Fuse link 10 Am(3) Earth spikes 1.2 (30) Earth spike 1.8 (8) Earth wire 6mm (300m) 70mm copper wire (10m) Coach srew (10) | MAK | 2025-02-12 | Tebello kalake | kalake@1pwrafrica.com
2025-02-20 17:43 | seshemane@1pwrafrica.com | Lefa seshemane | 1.2m earth spike=23 Steel pipe 20mm=30 Pvc conduit 20mm=25 Airdac =500m Earth resistance test =1 Bolt and nuts 6mm=30 Boro 22mm and 16mm | MAT | 2025-02-21 | LEBOHANG RALEKAOTA | Lebohang@1pwrafrica.com
2025-02-21 08:36 | lekhelebane@1pwrafrica.com | Rantso Lekhelebane | Bundle conductor Lv stay rod 5 Lv stay plate 5 | MAK | 2025-02-21 | Kalake | kalake@1pwrafrica.com
2025-03-26 09:12 | monoane@1pwrafrica.com | Sello Monoane | bulbs 12 | MAS | 2025-03-26 | Komete | komete@1pwrafrica.com
2025-05-19 09:41 | monaheng@1pwrafrica.com | Rethabile Monaheng | Airdec(one drum) Ready board(17) Earth Spike (24) | MAT | 2025-05-19 | Rethabile Monaheng | monaheng@1pwrafrica.com
2025-06-09 11:37 | teboho@1pwrafica.com | Teboho Noko | Airdac stariners 60 and 10 Suspensions | SHG | 2025-06-09 | Tiisetso Mahlehla | mahlela@1pwrafrica.com
2025-06-09 11:45 | teboho@1pwrafica.com | Teboho Noko | 6 MM black earth wire, 40 Airdac strainer and 10 Suspensions | MAS | 2025-06-09 | Mokhethi Komete | komete@1pwrafrica.com
2025-06-20 09:21 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Readyboard *1, meter*1 + c/b*1,airdac 40m,20mm*1 conduit, M12 *1 pigtail | MAK | 2025-06-20 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2025-06-24 12:53 | seshemane@1pwrafrica.com | Seshemane Lefa | House wire 6mm=200m Cable tie=2pck Airdac Strainers =30 T junction 20mm=20 Earth spikes 1.2m=10 Airdac =500m | MAT | 2025-06-24 | Rethabile Monaheng | monaheng@1pwrafrica.com
2025-07-01 17:46 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | TTD 201 =150, LV STAY WIRE= 200M, CABLE TIES= 2 PARKETS, ABC STRAINERS= 102, EARTH SPIKES 1.2M= 30, AIRDAG STRINERS= 250, LV GAY GRIPS= 110, M16 PIGTAILS= 30, 6MM LUGS= 100, LV STAY INULATORS= 32, LV STAY RODS= 12, LV STAY PLATES= 5, BUGLES= 200, BLACK WIRE 6MM= 2 ROLLS, 3 WAY JUNCTION BOX= 80, LV SUSPENSION= 100, STAY THIMBE=13, LV POLE TOPS= 15, READYBOARDS= 50 | SHG | 2025-06-18 | Tiisetso Mahlehla | mahlela@1pwrafrica.com
2025-07-02 11:16 | ramothule@1pwrafrica.com | Motiki Ramothule | Pigtails screw (17) Pigtails big (6) Pole top (45) Long rods (4) D shacle (26) U nails (2kg) Eye nut LV (16) Eye nut MV (20) Spindle (5) Rods 250 (10) Strainer LV (17) Strainer Airdac (20) Thimble clevis (22) Stay thimble (14) Binding strap (1) Suspension LV(26) TTD 201 (100) Stay wire (100M) Pigtails screw M12 (40) Guy grip MV (100) Guy grip LV (100) | KET | 2025-07-03 | Motiki Ramothule | ramothule@1pwrafrica.com
2025-07-02 11:17 | lekhelebane@1pwrafrica.com | Rantso Lekhelebane | TTD 201F*50 Lv pole top*30 Lv bundle suspension *27 M12 nuts*50 M12 pigtail*40 Guy grip lv*40 Mv guy grip*33 Lv eye nut*20 Lv bundle strainer*12 M20 eyenut*27 Airdag pigscrew*30 Airdag strainer*20 Mv Thimble clevis *21 Mv d shackles *26 U nails pack*3 Spindle *3 Thimble*3 | MAS | 2025-07-02 | Rantso Lekhelebane | lekhelebane@1pwrafrica.com
2025-07-02 11:44 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Ready board*1,airdac*50m, M12 pigtail*1, conduit 20mm *2. | MAK | 2025-07-02 | Kalake | kalake@1pwrafrica.com
2025-07-03 09:11 | monaheng@1pwrafrica.com | Rethabile Monaheng | Pig tail M16 (20) MV guy grip(30) D-sharkles(14) 350MM stuts(2) 250MM(70) Long rods(14) LV guy grip(60) Pigtail M12(40) Bundle trainers(12) Airder strainer(20) Suspension (29) Pig tail screws (17) Lv thimble(4) Eye nut M16 (42) Lv pole top(20) Lv stay wire(100M) Spindle (3) M12 nut(60) | MAT | 2025-07-03 | Monaheng | monaheng@1pwrafrica.com
2025-07-03 10:56 | monaheng@1pwrafrica.com | Rethabile Monaheng | Clobes(20) | MAT | 2025-07-03 | Monaheng | monaheng@1pwrafrica.com
2025-07-04 06:30 | ramothule@1pwrafrica.com | Motiki Ramothule | Stay rods LV (2) Stay rod MV(1) Stay insulators MV (3) Stay insulators LV (11) Stay plates LV(2) Stay plate MV(1) | KET | 2025-07-04 | Motiki Ramothule | ramothule@1pwrafrica.com
2025-07-04 09:49 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Pigtail M12 | MAK | 2025-07-04 | Makhoalinyane | makhoalinyane@1pwrafrica.com
2025-07-04 10:11 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac 25m | MAK | 2025-07-04 | Makhoalinyane | makhoalinyane@1pwrafrica.com
2025-07-07 09:53 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac 75m | MAK | 2025-07-07 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2025-07-07 10:26 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | M12 pigtail*1, airdac strainers*2, suspension*1 | MAK | 2025-07-07 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2025-07-08 09:49 | rethabile@1pwrafrica.com | Rethabile lebajoa | 25 PVC conduits M20 eye nut 15 Binding strap 1 stay wire lv 100m M16 and M19 drill bit | MAT | 2025-07-08 | lefa seshemane | seshemane@1pwrafrica.com
2025-07-08 12:40 | rethabile@1pwrafrica.com | Rethabile lebajoa | Chain block 0.75t Bundle strainer 15 Airdec strainer. 10 6mm house wire Black. 1 Earth spike 1.2m 20 | MAS | 2025-07-10 | komete mokhethi | komete@1pwrafrica.com
2025-07-09 14:55 | rethabile@1pwrafrica.com | Rethabile lebajoa | Bundle strainer. 12 M20 eye nut. 15 pig tail screw. 3t D shackles. 26 Thimble clevis. 18 M12 pig tail 40 ABC suspension. 28. Airdec strainer. 23 Base stay plate 23 stay wire. 100m House wire 6mm black. 1 roll | SHG | 2025-07-10 | Tiisetso Mahlehla | mahlela@1pwrafrica.com
2025-07-09 15:01 | rethabile@1pwrafrica.com | Rethabile lebajoa | Stay base plate | MAS | 2025-07-10 | komete mokhethi | komete@1pwrafrica.com
2025-07-09 16:23 | ralekaota@1pwrafrica.com | Lebohang Ralekaota | 1.stepup transformer=1 2.green/yellow 16mm=12.5m 3.Arrestor 6kva=3 4.Arrestor 12kva=6 5.dropout brackets=4 6.mustofor brackets=4 7.mustofer fuses=5 8mustofer holders=10 9 bare copper 70mm=60m 10.450mm threaded rods=5 11.brassing straps=6 12.long rods=20 13.250mm threaded rods=30 14.pin insulators=21 15.spindles=21 16.lv stay wire=100m 17.mv stay wire=100m 18.mv stay rods=26 19.mv stay plats=26 20.mv stay insulators=16 21.mv pole tops=26 22.earth spikes 1.5mm=24 23.earth spikes 1.2mm=10 24.35mm pre-insulated lugs=10 25.mv guy grip=90 26.dead ends=20 27.pg clamps=35 28.cable ties=1packet 29.abc strainers=38 30.lv stay thimble=10 31.mv thimble clevis=20 32.mv d shackles=20 33.lv suspensions=40 34.airdac strainers=40 35.pvc conduit pipes=1 36.6mm black wire=100m 37.pvc 20mm conduit pipes=24 38.m16 pig tale strews=20 39.lv guy grips=35 | KET | 2025-06-24 | ralekaota@1pwrafrica.com | ralekaota@1pwrafrica.com
2025-07-10 09:23 | komete@1pwrafrica.com | Mokhethi Komete | 40 steel pipes | MAS | 2025-07-10 | Mokhethi Komete | komete@1pwrafrica.com
2025-07-14 14:33 | teboho@1pwrafrica.com | Teboho Noko | 500m airdac for MAS | MAS | 2025-07-14 | Komete Mokhethi | komete@1pwrafrica.com
2025-07-15 12:07 | ralekaota@pwrafrica.com | Lebohang Ralekaota | Pin insulator 30pcs Guy grip (LV) 200PCS Long rods 48pcs Eye nut (MV) 7pcs U nail 2 packs Dead end 50pcs Spindle 24pcs PVC conduit 50mm 3pcs Pole top (MV) 4pcs Pole top (LV) 73 PG clamp 41pcs Stay wire (MV) 100 meters Stay wire (LV) 200 meters Stay insulator LV 2pcs TTD 151 23pcs Hole bore 19mm 2pcs Hole bore 16mm 2pcs Foam spray 2pcs LED lights 3pcs pole climbing shoes 1 pair X-arms=3 16kva/19000/240v transformer rock drill=1 250mm threaded rods=15 20mm steel pipes=15 20mm pvc conduit pipes=25 50mm pvc conduit pipes=5 25mm pvc conduit pipes=20 70mm green/yellow=40m 70mm bare copper wire=70m | KET | 2025-07-15 | LEBOHANG RALEKAOTA | ralekaota@1pwrafrica.com
2025-07-16 14:38 | ralekaota@1pwrafrica.com | LEBOHANG RALEKAOTA | AIRDACS=4 | KET | 2025-07-16 | LEBOHANG RALEKAOTA | ralekaota@1pwrafrica.com
2025-07-25 10:01 | ramothule@1pwrafrica.com | Motiki Ramothule | Airdac (500) ABC bundle (3000) Squarrel (4000) Stay rod MV (5) M16 pig tails (150) M16 eye nut (10) Strainer (90) Suspension (120) Airdac strainer (200) Pigtails screw (100) TTD 201 (200) TTD 151 (100) Strupbinding (5) Pvc conduit 20mm(200) Pvc conduit 25mm(30) Steel conduit (100) Stay plates LV (10) Cable ties(25) Saddle steel(5 PACs) Stay wire LV (100M) Back wire (600M) Guy grip LV (20) Dropout fuse holder(6) Dropout fuses 5A(6) Monstofa brackets (2) Bare cupper 70mm(100M) Green and yellow 70mm(32M) Bimetallic lug 70mm(6) | KET | 2025-07-25 | Motiki Ramothule | ramothule@1pwrafrica.com
2025-07-25 10:06 | ramothule@1pwrafrica.com | Motiki Ramothule | Arrestors 6kv(2) Arrestors 12kv(6) ? brackets (60) Pg clamps (32) Thimble LV(50) | KET | 2025-07-25 | Motiki Ramothule | ramothule@1pwrafrica.com
2025-07-25 10:16 | monaheng@1pwrafrica.com | Monaheng Rethabile | Airdec (2500M) ABC Bundle (7000M) Squarrel conductor(3000M) LV stay rods and plates(40) each MV Stay rods and plates(8)each M16 pig tails(103) ABC strainers(96) Airdec strainers(132) Pig tail screws(100) Binding strap (4pcs) PVC Conduit 20mm(150) PVC Conduit 25mm(20) Steel pipe 20mm(80) Cable ties(25packets) Steel saddles (4pcs) Lv stay wire(300M) Mv stay wire(100M) Transfomer(1) Black wire 6mm(300M) Lv guy grips(120) Drop out fuse holder(2) Drop out fuse 5A(2) Mosdofer brackets (1) Bare copper 70mm(50M) Green and yellow 70mm(16M) Biematalic lug 70mm(2) Arrestor 6kv (1) Arrestor 12kv(2) Question mark brackets (2) PG clambs(24) Steel nails(4kg) Lv thimbles(90) | MAT | 2025-07-26 | Monaheng | Monaheng@1pwrafrica.com
2025-07-25 10:37 | monaheng@1pwrafrica.com | Rethabile Monaheng | Stay insulatos(4) Dead ends(30) Earth spike (40) TTDs 151(60) TTDs 201(100) | MAT | 2025-07-26 | Monaheng | monaheng@1pwrafrica.com
2025-07-25 12:34 | rethabile@1pwrafrica.com | Rethabile lebajoa | Bolt pigtails 101 pole top 27 LV guy grip 174 stay wire 300 stay rods 57 stay plates. 35 stay thimble. 57 stay insulator 57 ABC strainers 88 M16 eye nut 35 ABC conductor 5500 | MAS | 2025-07-28 | komete mokhethi | komete@1pwrafrica.com
2025-07-25 21:54 | monaheng@1pwrafrica.com | Rethabile Monaheng | Eye nut M20(10) | MAT | 2025-07-26 | Monaheng | monaheng@1pwrafrica.com
2025-07-26 05:20 | ramothule@1pwrafrica.com | Motiki Ramothule | Eye nut MV (40) | KET | 2025-07-26 | Motiki Ramothule | ramothule@1pwrafrica.com
2025-07-26 09:27 | kalake@1pwrafrica.com | Tebello kalake | Jack hummer of a power pack (1) | MAT | 2025-07-26 | Tebello kalake | kalake@1pwrafrica.com
2025-07-26 10:28 | mahlehla@1pwrafrica.com | Tiisetso Mahlehla | Airdag 5050m, Bundle 5000m, Stay rod Lv 55, Lv stay plate 55, Lv pole top 55, Lv stay insulator 55, Lv stay thimble 55, m16 pigtail 100, m16 eye nut 40, Abc strainers 90, Abc suspension 60, Airdag strainers 100, pintail screw 60, 201 TTDS 100, 151 TTDS 100, readyboards 20, strap binding, pvc conduit 20mm 100, pvc conduit 25mm 20, steel conduit 20mm 70,cable ties 4pcs, saddle steel 2 pcs, stay wire lv 300m, gay grip lv 120, steel nails 2kg, end cap 50, pvc pipe 50mm 4m, | SHG | 2025-07-26 | Mahlehla | mahlela@1pwrafrica.com
2025-07-26 11:01 | monaheng@1pwrafrica.com | Rethabile Monaheng | Borrow M16(3) | MAT | 2025-07-26 | Monaheng | monaheng@1pwrafrica.com | All given | Yes
2025-08-05 12:41 | komete@1pwrafrica.com | Mokhethi Komete | Cable ties (5 porkets) Earth spike clamps (10) Pre insulated lugs 35mm (7) Pre insulated lugs 70 mm (4) Pin insulators (12) Pole top lv (50) Long rods (30) | MAS | 2025-07-29 | Mokhethi Komete | komete@1pwrafrica.com | All given | Yes
2025-08-05 16:32 | makhoalinyane@1pwrafrica.com | Makhoalinyane Teboho | pigtails bold M12*4,pigtail bold M16*4,eyes nuts M16*4,6MM black wire 20m,earth spikes 1.2m*6,conduict pipe 20mm*4,u nails*20,airdac strainers*10,cable ties *100,suspensions*4, | TLH | 2025-08-05 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com | All given | Yes
2025-08-05 16:41 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | airdac drum | TLH | 2025-08-05 | Makhoalinyane | makhoalinyane@1pwrafrica.com | All given | Yes
2025-08-05 16:59 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | TTD 151 *12 | TLH | 2025-08-05 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | All given | Yes
2025-08-08 11:00 | rethabile@1pwrafrica.com | Rethabile lebajoa | 16 kvA transformer Airdec 1000m Bundle 1500m TTD 151 80 steel nail. 4p pole top 35 Airdec strainers 100 copper lug. 10 Earth spike 1.2m. 10 | MAS | 2025-08-08 | Rethabile lebajoa | rethabile@1pwrafrica.com | All given | Yes
2025-08-11 08:53 | monaheng@1pwrafrica.com | Rethabile Monaheng | 6mm earth wire (200M) Lv stay rod (10) Lv stay plate (20) Lv guy grip(60) M16 pig tail(40) Binding strap (2) | MAT | 2025-08-11 | Rafube Pemane | pemane@1pwrafrica.com | All given | Yes
2025-08-11 10:39 | monaheng@1pwrafrica.com | Rethabile Monaheng | Cable ties(5packets) Steel nail(4packets) Binding strap(3) | MAT | 2025-08-11 | Rafube Pemane | pemane@1pwrafrica.com | All given | Yes
2025-08-11 13:29 | rethabile@1pwrafrica.com | Rethabile lebajoa | 12kvA arrestor 5 packets of cable ties | MAS | 2025-08-11 | Rethabile lebajoa | rethabile@1pwrafrica.com | All given | Yes
2025-08-12 17:54 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Cable ties 5pcs,, still nails 4 pcs | SHG | 2025-08-11 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-08-14 15:31 | ralekaota@1pwrafrica.com | LEBOHANG RALEKAOTA | twin ties 14,dead end 74,fuse links 9,cable ties 8packets,mv stay rods+plates 10,lv guy grip95,lv stay rods 26,lv stay insulators 30,mv eye nuts 30,bundle conductor 1000m,fox conductor 20000m,cable cutter | KET | 2025-08-07 | Lebohang Ralekaota | ralekaota@1pwrafrica.com | All given | Yes
2025-08-15 09:17 | ramothule@1pwrafrica.com | Motiki Ramothule | Thimble clevis (20) Eye nut MV (20) D shackles (20) | KET | 2025-08-15 | Motiki Ramothule | ramothule@1pwrafrica.com | All given | Yes
2025-08-18 09:04 | rethabile@1pwrafrica.com | Rethabile lebajoa | TTD 151 48 airdec strainer 100 | MAS | 2025-08-18 | Rethabile lebajoa | rethabile@1pwrafrica.com | All given | Yes
2025-08-18 10:10 | monaheng@1pwrafrica.com | Rethabile Monaheng | Lv pole top(25) 6mm earth wire(400M) Airdec strainers (60) Cable ties (4packets) TTDs 151 (56) Airdec (1000M) | MAT | 2025-08-18 | Rethabile Monaheng | monaheng@1pwrafrica.com | All given | Yes
2025-08-19 09:02 | kalake@1pwrafrica.com | Tebello kalake | Lv stay plates (10) Lv guy grips (75) M16 pigtails( 40) Cable ties (3 pck) | MAT | 2025-08-19 | Tebello kalake | kalake@1pwrafrica.com | All given | Yes
2025-08-19 09:22 | monaheng@1pwrafrica.com | Rethabile Monaheng | Earth spike 1.2M(30) | MAT | 2025-08-19 | Monaheng Rethabile | monaheng@1pwrafrica.com | All given | Yes
2025-08-20 15:29 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | M16 Pick tails *1, airdac 20m, spare meter + 80A breaker | MAK | 2025-08-20 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com | All given | Yes
2025-08-20 18:20 | mahlela@1pwrafrica.com | Mahlehla | 5 pcs of 6MM BLACK WIRE | SHG | 2025-08-21 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-08-20 18:22 | mahlela@1pwrafrica.com | Mahlehla | 5 pcs of 6MM BLACK WIRE | MAS | 2025-08-21 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-09-02 09:08 | monoane@1pwrafrica.com | Sello Monoane | Airdac 40m | MAK | 2025-09-02 | Makhoalinyane Teboho | makhoalinyane@1pwrafrica.com | All given | Yes
2025-09-03 08:29 | Monaheng@1pwrafrica.com | Rethabile Monaheng | Dead end(19) Guy grip Mv (4) Pole top Mv(1) | MAK | 2025-09-03 | Monaheng | monaheng@1pwrafrica.com | All given | Yes
2025-09-04 08:16 | monaheng@1pwrafrica.com | Rethabile Monaheng | Solid link (2) Solid link brackets (2) 250mm studs(3) 450mm studs(1) Mv eye nud(2) D-shackles(2) Tie trap(2) Lv pole top(1) Lv guy grips(3) Lv stay insulator(1) | MAK | 2025-09-04 | Monaheng | monaheng@1pwrafrica.com | All given | Yes
2025-09-08 12:29 | monoane@1pwrafrica.com | Sello Monoane | Hoses, regulator, gauge VFD, tanker's pad | MAT | 2025-09-08 | Seshemane Lefa | seshemane@1pwrafrica.com | All given | Yes
2025-09-08 12:46 | ramothule@1pwrafrica.com | Motiki Ramothule | Stay rods and Thier plates (13) Stay Insulators (5) Pig tails (20) Eye nuts (22) Cable ties pcs(3) Stay wire LV (110)M 10mm black wire (200)M 6mm black wire (200)M Saddles (176) Lugs 6mm (100) Still nails pcs (2) Airdac strainers (30) Pvc conduit 25mm (25) | KET | 2025-09-09 | Motiki Ramothule | ramothule@1pwrafrica.com | All given | Yes
2025-09-09 09:13 | Mpapea@1pwrafrica.com | James mpapea | Stay rod (20) Stay plate (8) Pigtail m20(40) 3 way junction box(20) Cable ties(5 pack) Wallplug (200) Terminal lug(100) Fridge (1) Microwave (1) | TOS | 2025-09-09 | James mpapea | mpapea@1pwrafrica.com | All given | Yes
2025-09-09 11:44 | mahlela@1pwrafrica.com | TIISETSO MAHLEHLA | Lv stay plats 14, Lv guy grip 59, 20 mm steel conduit 14, M16 pigtail 53, 500M bundle, Lv pole tops 24 | SHG | 2025-09-09 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-09-09 11:50 | petlane@1pwrafrica.com | Petlane Lekau | Guy grip 3/3.35. 21 Guy grip 7/4.35. 12 U nails. 3kg Pig tail M16. 30 Twin ties for fox. 10 Stay rod 3/3.35. 5 Stay plate 3/3.35 5 Earth spike clamp. 12 M20 × 250mm. 5 M20 eye nut. 12 Clevis themble. 8 6mm black wire. 200m Cable ties black. 5packets Drop out bracket. 2 Surge arrestor 12kv 2 Surge arrestor 6kv. 1 Bundle 500m. 1 Question mark brackets 2 | MAT | 2025-09-10 | Petlane | petlane@1pwrafrica.com | All given | Yes
2025-09-11 11:25 | jopi@1pwrafrica.com | Leoma Jopi | Dead ends21 Twin ties 28 | MAK | 2025-09-11 | Leoma Jopi | jopi@1pwrafrica.com | All given | Yes
2025-09-12 08:55 | seshemane@1pwrafrica.com | Seshemane Lefa | Rock drill | SHG | 2025-09-12 | Tiisetso Mahlehla | tiisetso@1pwrafrica.com | All given | Yes
2025-09-12 16:27 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | 300M bundle, 3 Lv stay rods and 25MM conduit × 25 | SHG | 2025-09-12 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-09-15 12:38 | seshemane@1pwrafrica.com | Seshemane Lefa | Earthspike 1.2m=30 | KET | 2025-09-15 | Motiki Ramothule | motiki@1pwrafrica.com | All given | Yes
2025-09-15 13:05 | monoane@1pwrafrica.com | Sello Monoane | Solar Cables 100m black and red | KET | 2025-09-15 | Makhoalinyane | makhoalinyane@1pwrafrica.com | Not given
2025-09-16 11:49 | seshemane@1pwrafrica.com | Lefa seshemane | LV POLE TOP =5 Lv guy grip=15 6mm black wire=200m Mostofar fuse=1 Rock drill=2 Lv stay wire=110m TTD 201 | MAT | 2025-09-16 | Seshemane Lefa | seshemane@1pwrafrica.com | All Given | Yes
2025-09-30 14:25 | mahlela@1pwrafrica.com | Tiisetso Mahlehla | Bundle 500m | SHG | 2025-09-29 | Mahlehla | mahlela@1pwrafrica.com | All given | Yes
2025-10-01 12:21 | monoane@1pwrafrica.com | Sello Monoane | Cable ties packet | SEH | 2025-10-01 | Makhoalinyane | makhoalinyane@1pwrafrica.com | All given | Yes
2025-10-10 08:14 | monaheng@1pwrafrica.com | Monaheng | Lv stay rod (10) Mv stay plate(10) M16 pig tails(12) Airdac strainers (10) | SEH | 2025-10-10 | Monaheng | monaheng@1pwrafrica.com | All Given | Yes
2025-10-10 09:41 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Stay plate*1(MV), M16 pigtail*1,ABC bundle*70m,LV stay rod*1,TTD*8,couch screw *2 | MAK | 2025-10-10 | Thakholi | thakholi@1pwrafrica.com | All Given | Yes
2025-10-12 22:10 | mahlela@1pwrafrica.com | Mahlehla Tiisetso | 1706 Meters Bundle | SHG | 2025-10-07 | Mahlehla | mahlela@1pwrafrica.com | All Given | Yes
2025-10-14 11:00 | lekhelebane@1pwrafrica.com | Rantso Lekhelebane | Transformer1 Mosdorfer 3 Question mark bracket*2 Long rods 13 Steel pipe 20mm*10 PG clamps*15 Earth spike clamp*10 Mosdorfer fuse *3 Steel nail pack 1 Threatened rod 250mm *2 Threatened rod 350mm *3 Earth spike 1.5 *8 Earth spike 1.2 *8 TTD 16 Bidding Buckles *150 Binding strap*5 G/Y Earth wire 70mm 15m saddles *90 Wire 6mm 100m Drop out *2 Drop out fuse link *2 Fuse link*4 Surgery arrestor12 *1 | MAK | 2025-10-14 | Rantso Lekhelebane | lekhelebane@1pwrafrica.com | All Given | Yes
2025-10-15 06:08 | mahlela@1pwrafrica.com | Mahlehla Tiisetso | Earth spike 1.2M×40, 8mm CNE Airdag 500m | SHG | 2025-10-15 | Mahlehla | mahlela@1pwrafrica.com | All Given | Yes
2025-10-15 12:18 | mahlela@1pwrafrica.com | Mahlehla Tiisetso | 6mm black wire 500M | SHG | 2025-10-15 | Mahlehla | mahlela@1pwrafrica.com | All Given | Yes
2025-10-21 09:25 | rethabile@1pwrafrica.com | Rethabile lebajoa | Bundle drum 1706 | MAS | 2025-10-21 | Rethabile lebajoa | rethabile@1pwrafrica.com | All Given | Yes
2025-10-22 14:08 | jopi@1pwrafrica.com | Leoma Jopi | gripping tool(1) Earth resistance testor (1) Ttds 16 Pre insulated lug 35mm*10, 75mm*3 Pin type insulators 9 Fuse links 10A*4 Tin ties 10 Cable ties 2packets M16 pigtails*3 | MAK | 2025-10-22 | Jopi | jopi@1pwrafrica.com | All Given | Yes
2025-10-23 07:46 | rethabile@1pwrafrica.com | Rethabile lebajoa | Airdac 1532m earth spikes 1.2. *30 | MAK | 2025-10-15 | Rantso lekhelebane | rantso@1pwrafrica.com | All Given | Yes
2025-12-01 12:58 | komete@1pwrafrica.com | MOKHETHI KOMETE | 4 pounds hammers (2) Chisels (2) | SEB | 2025-11-26 | MOKHETHI KOMETE | komete@1pwrafrica.com | All Given | Yes
2025-12-02 17:50 | mahlela@1pwrafrica.com | Mahlehla | Pole box Single channel 26, 2 channel 8, 3 channel 6, 4 channel 4, Pvc conduit 25mm 25, steel saddle 20mm 2 parkets, Airdac strainers 120, strap binding 1 parket, cable ties 2 parkets | SHG | 2025-11-28 | Mahlehla | mahlela@1pwrafrica.com | All Given | Yes
2025-12-07 15:31 | petlane@1pwrafrica.com | Petlane Lekau | Single channel 10 2 channel. 2 3 channel. 4 4 channel 3 | MAT | 2025-11-28 | Petlane Lekau | petlane@1pwrafrica.com | All Given | Yes
2025-12-10 08:11 | makhoalinyane@1pwrafrica.com | Teboho Makhoalinyane | Airdac strainers (12), suspensions(4), 12mm pigtails (6),airdac roll,20mm conduit pipes(5),LV stay assemble (1),TTDs (16),6mm black cable(50m),still nails (30), fisher plugs(30),cable ties(100). | TLH | 2025-12-10 | Makhoalinyane | makhoalinyane@1pwrafrica.com | All Given | Yes
2025-12-11 10:49 | jopi@1pwrafrica.com | Leoma Jopi | Bundle200m Strainers 4 M12 pig tails 48 1.2 spikes 30 Single channel 11 Double 4 3channel 1 Saddles 2packets Ready boards12 Steal conduits 11 Guy grips 10 6mm black wire 100m Airdac strainers 120 | MAK | 2025-12-08 | Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-01-09 09:16 | rethabile@1pwrafrica.com | Rethabile Lebajoa | lug 6mm * 200 | MAK | 2026-01-08 | Tsietsi Lejakane | lejakane@1pwrafrica.com | All Given | Yes
2026-01-14 16:53 | jamesmpapea2@gmail.com | James mpapea | Threaded rod M20 450mm*8 Threaded rod M16 350mm*1 Threaded rod M20 650mm*2 Threaded rod M20 250mm*12 Fuse link 8 Amps *6 Coach screws*10 | KET | 2026-01-15 | Mpapea james | jamesmpapea2@gmail.com | All Given | Yes
2026-01-21 08:02 | jopi@1pwrafrica.com | Leoma Jopi | Airdec strainer50 6mm Earth wire 100m*2 1.2m Earth spikes*50 3way junction boxes 2packets 20mm couplers 1packet End caps 30 | MAK | 2026-01-20 | Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-01-26 08:46 | moletsane@1pwrafrica.com | Rebusoajoang Moletsane | Tracker Motor (1) | MAK | 2026-01-26 | Teboho Makhoalinyane | makhoalinyane@1pwrafrica.com
2026-01-26 10:28 | teboho@1pwrafrica.com | Teboho Noko | 5 x M12 pigtail bolts and Nuts with 1 x M8 pigtail screw, 6 x ready boards and 6 mm Black house wire | MAK | 2026-01-26 | Jopi Leoma | jopi@1pwrafrica.com | All Given | Yes
2026-01-29 11:45 | jopi@1pwrafrica.com | Leoma Jopi | Readyboards(6) Cable ties (10pkts) | MAK | 2026-01-28 | Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-01-30 16:45 | ramothule@1pwrafrica.com | Motiki Ramothule | Step up TRM (1) 180KVA Step down TRM (3) 25KVA Surge arestors 24KV (15) Surge arestors 6KV (4) Drop out fuses 5A (14) Machanele 2.5M (10) Machanele 0.9 (16) Mostophor fuses 60A (8) Rods 250mm (6) Rods 350mm (12) Rods 450mm (4) Rods M16*250mm (16) Cross arm 2.5M (4) Drop out brackets (2) Drop out (2) L bracket (2) | KET | 2026-01-31 | Motiki Ramothule | ramothule@1pwrafrica.com | All Given | Yes
2026-02-12 15:43 | ramothule@1pwrafrica.com | Motiki Ramothule | Lugs 70*12(40) Bimetallic lugs 35(8) Boro 22mm(1) | KET | 2026-02-13 | Motiki Ramothule | ramothule@1pwrafrica.com | All Given | Yes
2026-03-03 16:26 | pebane@1pwrafrica.com | Pebane Retselisitsoe | Diesel Heater (1) | TLH | 2026-03-04 | Retselisitsoe Pebane | pebane@1pwrafrica.com | All Given | Yes
2026-03-04 09:15 | pebane@1pwrafrica.con | Retselisitsoe Pebane | Generator air filter(1) and thread seal (1) | TLH | 2026-03-04 | Retselisitsoe Pebane | pebane@1pwrafrica.com | All Given | Yes
2026-03-12 10:27 | monaheng@1pwrafrica.com | Rethabile Monaheng | Steel nails (1 packet) 6mm earth wire (100M) | SEH | 2026-03-12 | Monaheng | monaheng@1pwrafrica.com | All Given | Yes
2026-03-12 10:36 | monaheng@1pwrafrica.com | Rethabile Monaheng | Climbing shoes | SEH | 2026-03-12 | Monaheng | monaheng@1pwrafrica.com | All Given | Yes
2026-03-13 09:49 | seshemane@1pwrafrica.com | Lefa Seshemane | Link stick Earth kit | KET | 2026-03-13 | Motiki | motiki@1pwrafrica.com | All Given | Yes
2026-03-13 10:35 | seshemane@1pwrafrica.com | Lefa Seshemane | 16mmx16mm lugs (20),70mmx12 lug (20) | KET | 2026-03-13 | Motiki@1pwrafrica.com | ramothule@1pwrafrica.com | All Given | Yes
2026-03-13 11:21 | seshemane@1pwrafrica.com | Lefa Seshemane | Eath resident test | KET | 2026-03-13 | Motiki | ramothule@1pwrafrica.com | All Given | Yes
2026-03-24 10:17 | seshemane@1pwrafrica.com | Lefa Seshemane | M16 nuts =20 16mmx16mm lugs =20 Complete drop out =2 Drop out fuse 5A=15 | KET | 2026-03-16 | Motiki | motiki@1pwrafrica.com | All Given | Yes
2026-03-24 18:20 | jopi@1pwrafrica.com | Leoma Jopi | 3channel enclosures(4), ABC Bundle(300m) | MAK | 2026-03-23 | Leoma Jopi | jooi@1pwrafrica.com | All Given | Yes
2026-04-08 15:18 | rethabile@1pwrafrica.com | Rethabile lebajoa | Stay rod lv 32 Stay plate lv 32 ABC strainer 50 Pole top lv 32 Lv guy grip 96 M16 pig tail 50 | MAS | 2026-04-07 | Mosehle mokoatle | mosehle@1pwrafrica.com | All Given | Yes
2026-04-08 15:22 | rethabile@1pwrafrica.com | Rethabile lebajoa | House wire black 6mm * 6 Airdec strainer 120 | MAS | 2026-04-08 | Mosehle mokoatle | mosehle@1pwrafrica.com | All Given | Yes
2026-04-09 08:44 | komete@1pwrafrica.com | Mokhethi Komete | Airdac (100m) Copper wire 6mm (500m) Airdac strains clamps (153) Earth spikes 1.2m 100 U nailes (4kg) ABC conductor single phase (1706m×2) Stayrods lv (40) Stay plates lv (40) Guy grips lv (120) Pole top lv (40) Stay vimble (40) Pig tails M16 (60) Strain clamps ABC (50) Pig tails M12 (80) Pre insulated lugs 35mm (6) Band it strap (17) Steel nails (2kg) End caps (50) Steel saddles (200) Eye nuts M16 (100) Lugs 6mm (100) Prop bracket (1) Drill bit 22mm (1) Drill bit 19mm (2) Buckles (200) | TOS | 2026-04-09 | Mokhethi Komete | komete@1pwrafrica.com | not given | Yes
2026-04-10 08:40 | komete@1pwrafrica.com | Mokhethi Komete | Stay rods lv (40) Stay plates lv (40) Stay vimble (100) End caps (50) 6×6 lugs (100) 12×12 lugs (100) Pole tops lv (40) Pig tails M16 (60) Pig tails M12 (80) Cable ties 4 pockets (400) Steel saddles (200) U nailes (4kg) Steel nails (2kg) 6 mm earth wire (300m) Eye nuts M16 (100) Guader bolts (100) Guy grips lv (120) | TOS | 2026-04-09 | Mokhethi Komete | komete@1pwrafrica.com | All Given | Yes
2026-04-13 09:05 | jopi@1pwrafrica.com | LeomaJopi | Pole top LV (40) Stay plates LV (33) Stay rods LV (33) Guy grips Lv (100) Pigtails M16 (40) M12 (80) Eye nut M16(100) ABC stainers (50) Cable tie (4pts) Tjunctions (86) 6mm Earth 100*2 U nails 4pts End caps (84) Steel nails 1pt Earth spikes 1.2m (60) PVC conduits 20mm(14) 59mm(1) Bundle conductor (1706m) | MAK | 2026-04-06 | Leoma Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-04-13 11:35 | ramothule@1pwrafrica.com | Motiki Ramothule | ABC (bundle) 1706M Airdac 1000M Stay plates LV (40) Stay rods LV (40) Guy grips LV (120) Earth spikes 1.2M (80) Bold and nuts 6mm (100) Lugs 6*8mm (120) Earth spikes clamps (200) Poletop LV (40) Strainers LV (100) Strainers Airdac (240) U-nails 4packets Steel nail 4packets Cable ties big (6) Cable ties small (4) Pigtails M16 (120) Pigtails M12 (160) | SEH | 2026-04-14 | Monaheng Rethabile | monaheng@1pwrafrica.com | All Given | Yes
2026-04-17 11:14 | makoetje@1pwrafrica.com | Lebusa Makoetje | Strapping 5boxes U-nail 3packets Buckles 300 ea ABC strainers 100 ea Airdac strainers 240 ea Pole top make-off 56 LV, ea ABC suspension 12 ea Airdac 1000m 20mm steel conduit 20ea Earth spike 1.2m 160pcs 20mm T-junction 80pcs 6mm earthing wire 100m Earth spike clamp 160 ABC Bundle 3412m | TOS | 2026-04-17 | Komete Mokhethi | komete@1pwrafrica.com | All Given | Yes
2026-04-22 13:56 | makhoalinyanetseko@gmail.com | Makhoalinyane Teboho | MC4s *8 | KET | 2026-04-22 | Teboho Makhoalinyane | makhoalinyanetseko@gmail.com | All Given | Yes
2026-04-22 14:16 | makhoalinyanetseko@gmail.com | Makhoalinyane Teboho | Earth spike *4,U nails 1kg,cable ties*100,6mm *100m, binding strap* 30m,buckles * 8, earth sticks clamps *8 | KET | 2026-04-22 | Teboho Makhoalinyane | makhoalinyanetseko@gmail.com | All Given | Yes
2026-04-27 13:38 | Jopi@1pwrafrica.com | Leoma Jopi | Airdac (2) rolls | MAK | 2026-04-27 | Leoma Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-04-28 09:17 | jopi@1pwrafrica.com | Leoma Jopi | 20mm saddle (1 pkt) | MAK | 2026-04-28 | Leoma Jopi | jopi@1pwrafrica.com | All Given | Yes
2026-04-28 10:16 | kalake@1pwrafrica.com | Tebello kalake | Cable ties(6 packets) Lv stay insulator(50) | MAS | 2026-04-17 | Tiisetso Mahlehla | Mahlehla@1pwrafrica.com | All Given | Yes
2026-05-02 08:03 | thakholi@1pwrafrica.com | Katleho Thakholi | Meter box single channel, MAS 073 , containing meter with number SMRSD-04-0002FD55 and another meter box MAS -078 Containing meter with number SMRSD-04-00029907 | KET | 2026-05-02 | Katleho Thakholi | thakholi@1pwrafrica.com
2026-05-02 09:42 | thakholi@1pwrafrica.com | Katleho Thakholi | Diesel heater(2) tag numbets 1PWR00554 & 1PWR00547 Diesel fuel mixture 20L x2 | KET | 2026-05-02 | Katleho Thakholi | thakholi@1pwrafrica.com
2026-05-04 11:26 | ralekaota@1pwrafrica.com | Lebohang Ralekaota | Pigtale screws 50 Gutter bolt and nuts 100 Square washer M16 *20 M16 nuts*60 Guy grip lv*100 201 TTDs *80 151 TTD*80 Steel nail*2 packets 3packet cable ties 35mm lugs(pre insulated)*1packet | TOS | 2026-05-05 | Lebohang Ralekaota | Ralekaota@1pwrafrica.com
2026-05-04 11:44 | monaheng@1pwrafrica.com | Rethabile Monaheng | Pig tale screws 60 Square washer M16 *20 (100) M16 nuts*(100) 201 TTDs (40) 151 TTD (200) Lv Stay wire (100M) 20mm Conduit PVC (25) 25mm Conduit pvc(1) Tie strap (2 packets) Bugles(1packet) | SEH | 2026-05-04 | Monaheng | monaheng@1pwrafrica.com
2026-05-06 11:34 | Ralekaota@1pwrafrica.com | Lebohang Ralekaota | Bundle*1700m Airdac *1 Lv bracket*1 Lv(ABC) suspension *50 | TOS | 2026-05-05 | Ralekaota@1pwrafrica.com | Ralekaota@1pwrafrica.com

## Detailed Approval Records Formp
Timestamp | Response Id | Request # | Revision # | Overall Status | Requestor | Edit Response Url | Total Recipients | Participant Ids | Recipient 1 | Recipient 1 Status | Recipient 1 Issue Date | Recipient 1 Response Date | Recipient 1 Comment | Recipient 1 Settings | Recipient 2 | Recipient 2 Status | Recipient 2 Issue Date | Recipient 2 Response Date | Recipient 2 Comment | Recipient 2 Settings | Recipient 3 | Recipient 3 Status | Recipient 3 Issue Date | Recipient 3 Response Date | Recipient 3 Comment | Recipient 3 Settings | Recipient 4 | Recipient 4 Status | Recipient 4 Issue Date | Recipient 4 Response Date | Recipient 4 Comment | Recipient 4 Settings | Recipient 5 | Recipient 5 Status | Recipient 5 Issue Date | Recipient 5 Response Date | Recipient 5 Comment | Recipient 5 Settings | Recipient 6 | Recipient 6 Status | Recipient 6 Issue Date | Recipient 6 Response Date | Recipient 6 Comment | Recipient 6 Settings | Recipient 7 | Recipient 7 Status | Recipient 7 Issue Date | Recipient 7 Response Date | Recipient 7 Comment | Recipient 7 Settings | Recipient 8 | Recipient 8 Status | Recipient 8 Issue Date | Recipient 8 Response Date | Recipient 8 Comment | Recipient 8 Settings | Recipient 9 | Recipient 9 Status | Recipient 9 Issue Date | Recipient 9 Response Date | Recipient 9 Comment | Recipient 9 Settings | Recipient 10 | Recipient 10 Status | Recipient 10 Issue Date | Recipient 10 Response Date | Recipient 10 Comment | Recipient 10 Settings